QCI Central Finite Curve

Production Implementation Plan — IT Evaluation Brief

Background & Purpose

Central Finite Curve is a RAG-powered document generation platform being built for QCI. It ingests institutional documents (Work Orders, Proposals, Reports) and enables staff to generate new drafts grounded in prior work. A working demo was validated on 23 April 2026 with 24 documents on Railway PaaS.

This brief is for IT team evaluation. Three infrastructure options are presented below. IT is requested to assess compliance feasibility, flag any blockers (especially on data residency and VPN), and provide inputs before senior leadership review.

Demo vs. Production Gap

The demo environment is not representative of production scale:

| Component | Demo State | Production Requirement |
| --- | --- | --- |
| Documents | 24 PDFs (~50 MB) | ~80 GB corpus (thousands of docs) |
| Concurrent Users | 1–3 | ~500 |
| Auth | Shared password + JWT | SSO / RBAC |
| OCR | RunPulse free tier | Enterprise / Docling hybrid |
| Database | Railway Postgres (basic) | Managed, HA, with backups |
| Storage | Railway volume mount | S3-compatible blob storage (India region) |
| LLM | Gemini Flash free tier | Paid tier or alternative |

Key Technical Decision Areas — IT Input Required

The following areas require IT sign-off before implementation begins:

| Area | Core Question | Direction |
| --- | --- | --- |
| OCR | RunPulse enterprise vs open-source? | Docling (bulk) + RunPulse for new docs only |
| Hosting | Railway vs Azure/AWS? | Azure Central India (data residency) |
| Database | Railway Postgres vs managed? | Azure PostgreSQL Flexible Server + pgvector |
| Security / VPN | How to ingest QCI server docs safely? | Site-to-site VPN, read-only mount, audit logs |
| LLM | Paid vs free tier? | Gemini Flash paid tier (<₹5K/mo at scale) |
| Dev Tooling | AI coding access? | Cursor Ultra ($200/mo) — all models, full agents |

DATA RESIDENCY: QCI is a government body. Railway hosts data on US/EU servers only. If QCI IT security policy requires data to remain in India, Option A is disqualified and Option B (Azure Central India) or Option C (AWS Mumbai) is mandatory.

VPN (CRITICAL PATH): Ongoing document ingestion from QCI's local server requires a site-to-site VPN configured by QCI IT (read-only mount). This is on the critical path for all options. A manual upload interim is available while VPN is set up.

Options A, B, and C follow on the next three pages

Option A — Lean Production (Railway + Incremental Hardening)

"Ship fast, harden later"

Stay on Railway Enterprise, add proper auth and monitoring. Fastest and cheapest path. Data residency compliance must be confirmed by IT before selecting this option.

Architecture

| Component | Detail |
| --- | --- |
| Hosting | Railway Pro/Enterprise — currently in use; upgrade to Enterprise plan |
| Database | Railway Postgres with backups enabled |
| OCR | Docling open-source (bulk ingest) + RunPulse (new documents only) |
| LLM | Gemini Flash (paid tier) |
| Auth | JWT with user accounts (no SSO in this phase) |
| VPN | WireGuard tunnel to QCI local server (QCI IT to configure) |
| Frontend | Vercel free tier or Railway static hosting |
| Dev Tooling | Cursor Ultra ($200/mo) — all frontier models, full agent mode |

Budget

| Category | Best Case | Normal Case | Worst Case |
| --- | --- | --- | --- |
| Railway hosting | ₹5K/mo | ₹12K/mo | ₹25K/mo |
| RunPulse OCR (ongoing) | ₹15K/mo | ₹40K/mo | ₹80K/mo |
| Gemini API (LLM generation) | ₹500/mo | ₹2K/mo | ₹5K/mo |
| Cursor Ultra (dev tooling) | ₹17K/mo | ₹17K/mo | ₹17K/mo |
| Domain + SSL | ₹500/mo | ₹500/mo | ₹500/mo |
| Monthly Total | ₹38K | ₹71.5K | ₹1.27L |
| One-time setup | ₹50K | ₹1L | ₹2L |
| Year 1 Total | ₹5.1L | ₹9.6L | ₹17.2L |

Trade-offs

Advantages

- Fastest path to production: 4–6 weeks

- Lowest one-time setup cost

- Buildable with Cursor Ultra; QCI IT involvement minimal (VPN + domain only)

Limitations

- Data hosted on US/EU servers — may fail QCI IT security or compliance audit

- No SSO or enterprise compliance features in initial phase

- Prabhav cannot run DARPG work in parallel (for the build phase)

- ⚠ IT team to verify Railway data residency compliance before selecting this option

| Timeline | 4–6 weeks (best) · 6–8 weeks (worst) |
| --- | --- |
| Staffing | Prabhav (primary developer) + QCI IT (VPN setup and domain pointing only) |

Option B — Azure India Hybrid ★ Recommended

"Government-ready without over-engineering"

Move compute and database to Azure Central India for data residency. Use managed Azure services to minimise operational burden. Integrates with QCI's existing Microsoft stack.

Architecture

| Component | Detail |
| --- | --- |
| Hosting | Azure App Service (B2 plan, 2 instances) — Central India region |
| Database | Azure Database for PostgreSQL Flexible Server + pgvector extension |
| OCR | Docling open-source (bulk ingest) + Azure Document Intelligence (new docs) |
| LLM | Gemini Flash via API (or Azure OpenAI for full data-in-Azure compliance) |
| Auth | Azure AD B2C / QCI’s existing SSO infrastructure |
| VPN | Azure VPN Gateway → QCI local server (managed, enterprise-grade) |
| Storage | Azure Blob Storage (India region) |
| Dev Tooling | Cursor Ultra ($200/mo) — all frontier models, full agent mode |

Budget

| Category | Best Case | Normal Case | Worst Case |
| --- | --- | --- | --- |
| Azure Compute (App Service) | ₹8K/mo | ₹18K/mo | ₹35K/mo |
| Azure PostgreSQL Flexible Server | ₹5K/mo | ₹10K/mo | ₹20K/mo |
| Azure Blob Storage | ₹500/mo | ₹1.5K/mo | ₹3K/mo |
| Azure VPN Gateway | ₹3K/mo | ₹3K/mo | ₹5K/mo |
| OCR (Azure Document Intelligence) | ₹2K/mo | ₹5K/mo | ₹15K/mo |
| LLM API (Gemini / OpenAI) | ₹500/mo | ₹3K/mo | ₹8K/mo |
| Cursor Ultra (dev tooling) | ₹17K/mo | ₹17K/mo | ₹17K/mo |
| Monitoring + misc. | ₹1K/mo | ₹2K/mo | ₹5K/mo |
| Monthly Total | ₹37K | ₹59.5K | ₹1.08L |
| One-time setup | ₹1.5L | ₹3L | ₹5L |
| Year 1 Total | ₹5.9L | ₹10.1L | ₹18L |

Trade-offs

Advantages

- Data residency in India — meets government compliance requirements

- Azure AD integration enables SSO with QCI’s existing infrastructure

- Managed services minimise ongoing maintenance overhead

- Azure Hybrid Benefit (if QCI has M365 licensing) can reduce compute costs 30–40%

Limitations

- More setup complexity than Railway (8–12 weeks vs 4–6 weeks)

- Prabhav cannot run DARPG work in parallel during Azure buildout phase

- ⚠ Optional: Azure consultant for 2–3 weeks (₹50K–1L) would significantly accelerate initial setup

| Timeline | 8–10 weeks (best) · 12–14 weeks (worst) |
| --- | --- |
| Staffing | Prabhav (primary, ~80% of build) + QCI IT (Azure subscription, VPN, AD integration, security review) + optional Azure consultant (2–3 weeks part-time) |

Option C — Full Enterprise (Dedicated Infrastructure + Ops Team)

"Maximum control, maximum cost"

Full cloud deployment on Kubernetes with a dedicated DevOps engineer, CI/CD pipeline, staging environment, self-hosted OCR, and comprehensive monitoring. Included for completeness — represents production-grade infrastructure for a large government IT deployment.

Architecture

| Component | Detail |
| --- | --- |
| Hosting | Azure AKS (Kubernetes) or AWS ECS — full container orchestration |
| Database | Azure PostgreSQL HA (zone-redundant, automated failover) |
| OCR | Self-hosted Docling on dedicated GPU instances |
| LLM | Azure OpenAI (data stays entirely within Azure boundary) |
| Auth | Full SSO with RBAC, MFA, and conditional access policies |
| CI/CD | GitHub Actions → staging environment → production pipeline |
| Monitoring | Azure Monitor + Application Insights + alerting rules |
| Security | External security audit, penetration testing, WAF |

Budget

| Category | Best Case | Normal Case | Worst Case |
| --- | --- | --- | --- |
| Azure Infrastructure (AKS/ECS) | ₹40K/mo | ₹80K/mo | ₹1.5L/mo |
| DevOps Engineer (contract hire) | ₹80K/mo | ₹1.2L/mo | ₹1.5L/mo |
| GPU Compute (self-hosted OCR) | ₹15K/mo | ₹30K/mo | ₹50K/mo |
| LLM API (Azure OpenAI) | ₹3K/mo | ₹8K/mo | ₹20K/mo |
| Monitoring + security tools | ₹5K/mo | ₹10K/mo | ₹20K/mo |
| Monthly Total | ₹1.43L | ₹2.48L | ₹3.9L |
| One-time setup | ₹5L | ₹10L | ₹15L |
| Year 1 Total | ₹22L | ₹40L | ₹62L |

Trade-offs

Advantages

- Maximum security, compliance, and operational control

- Full high-availability and disaster recovery

- Production-grade CI/CD with staging environment

- Comprehensive monitoring and alerting infrastructure

Limitations

- Highest cost — 4–6× Option B Year 1 budget

- Requires a dedicated DevOps hire (cannot be built solo)

- Over-engineered for current ~500 user base

- Longest timeline: 16–24 weeks minimum

| Timeline | 16 weeks (best) · 20–24 weeks (worst) |
| --- | --- |
| Staffing | Prabhav + Dedicated DevOps Engineer (full-time) + QCI IT (active) + External Security Auditor |

★ IT Evaluation Requested: Data residency policy applicability · Azure subscription provisioning path · VPN feasibility with QCI network team · SSO / Azure AD integration scope · Security audit requirements. Please flag any blockers to Option B before leadership presentation.