Proposal for the Socio-economic Profiling of PM-SVANidhi Beneficiaries and their families (Extension) (2025-26)

Quality Council of India

## August 2025

1

# Contents

### Summary of SVANidhi se Samriddhi Engagement - for 3612 ULBs	2

  - Design and Training

  - Tech Development

  - Field Support

  - Analytics and Report

### Proposal Background (Extension) (2025-26)	4

  - QCI’s Objective and Engagement

### Key Deliverables	4

### Methodology	5

  - Support, maintenance, upgrades, modifications or new releases of the Software Extension

  - Training

  - Data collection

  - Analysis and Report

### Project Timeline	7

- Project Management Unit (PMU)	8

- Regional/ State Coordinator, Quality Check & Trainer 	8

- IT Team & Infra Components	9

- Handover and Knowledge Transfer Plan	14

- Manpower and Commercial	15

- Terms of Payment	16

Annexure 1	17

Annexure 2	19

# Summary of SVANidhi Se Samriddhi (Phase I – VII)

# Engagement – For 3612 ULBs

Design and Training

- Developing methodology for “Socio Economic Profiling”, QCI team has successfully developed

Questionnaire for socio-economic profiling and linkages for selected central schemes.

- Currently the programme is implemented in 3612 ULBs. The implementation of programme took place in phase-wise manner between (2020 – 2025):

    - Phase I – 127 ULBs

    - Phase II – 126 ULBs

    - Phase III – 1601 ULBs

    - Phase IV – 163 ULBs

    - Phase V – 1192 ULBs

    - Phase V (Extension) – 305 ULBs

    - Phase VI – 50 ULBs

    - Phase VII – 48 ULBs

- Designed and developed training plan at ULB level.

- Provided hands on training to the ULB officials and CLNOs.

- Refresher training is provided to ULBs & CLNOs on monthly basis. Trainings are also scheduled for the ULBs, as per requirement.

Tech Development

- Development of technology platform for profiling and checking the eligibility of the vendors and their family members, as well as linking them with eligible schemes with the help of CLNO logins.

- User friendly interface which allows the user to easily navigate the portal and export data dump in an Excel / CSV format for analysis. Developed user portals for different stakeholders.

- Visual dashboard available to public gives the overall, State and ULB-wise summary along with the map feature.

- OTP functionality is added in which, on selecting a new form an OTP will be generated on vendor’s mobile number or on vendor’s alternative number, and the profiling will be started post OTP verification.

- QC Functionality is developed with three stages: QC pending, Flagged, and data received.

- Hard and systems checks are implemented in the system while profiling of Street vendors.

- Once the profiling is submitted, the status of the form will change to QC Pending. In case any errors/ discrepancies are found, the form will be flagged by QCI team.

Field Support

- RCs provided the support (query resolution, on-call training) to all the stakeholders that were part of profiling and scheme linkages, and also provided them with best practices that they can adapt during data collection

- Encouraging the ULBs and CLNOs for profiling and scheme linkages in order to reach maximum beneficiaries

Analytics and Report

  - Report and Data analytics- Monthly reports and other analysis such as profiling status, scheme related analysis and street food vendors’ details etc.

  - Day to day analysis such as camp status, profiling status, and scheme related etc. as per the requirement

# Proposal background (Extension) (2025-26)

From 2020-25, QCI was engaged as an implementation partner for conducting the socio-economic profiling of PM SVANidhi beneficiaries and their families in 3612 ULBs. To date, more than 46.50 lakh PM SVANidhi beneficiaries have been profiled along with their 98.80 lakh family members with 1.38 Cr Scheme Linkages across beneficiaries under eight central schemes.

Further MoHUA intends to expand this program for additional PM SVANidhi beneficiaries in total approximately 4500+ ULBs. Under this scheme approximately 60 lakh beneficiaries (tentative, this is an incremental number, and progressively increases with increase in first term SVANidhi loan) will be profiled & eligible beneficiaries will get sanctioned under eight central schemes till March 2026.

## QCI’s Engagement and Objectives for (Extension) (2025-26) of SVANidhi Se Samriddhi Project

The objective of the project is to further assist the Ministry of Housing and Urban Affairs (MoHUA) in preparing the socio-economic profiles and scheme linkages for PM SVANidhi beneficiaries along with their family members till March’26 in total 4500+ ULBs (Scope as indicated above).

# Key Deliverables

| S.No. | Deliverables | Details |
| --- | --- | --- |
| 1. | Training | - ULB admins, who will follow the Train the Trainer (TTT) Model to ensure that people working on ground and new data enumerators (if any) - CLNOs, from all in line- Ministries & departments |
| 2. | Optimization, Development, Maintenance and support of technology tool | - Application: Web application to conduct vendor profiling, QC flagging, Editing, evaluation of scheme linkages. Web Application also to be made available for Nodal Officers for updating of scheme status to applied, sanction or rejected - Mobile Application to conduct profiling of street vendor. Mobile app feature also available for ULB official to capture camp details and for Nodal officers to update scheme status - Web Application – Admin features like SVA Tracker, ULB Tracker, State Tracker and view of Camp Details. |

|  |  | - Dashboard: Dashboard for all stakeholders to track the progress of program as per their role and access rights - An Editing tool will be provided to ULBs for editing of Family details of the vendor. Only new family details can be edited through this tool. - Maintenance and support of IT tool |
| --- | --- | --- |
| 3. | Data Analysis and Report Submission | Detailed analysis will be done by QCI to focus on key findings of the assessment, and will be submitted in the form of: - Monthly Report - Quarterly report - Final Report, highlighting the state/ ULB wise data Reports in the format provided by MoHUA to be added to all Logins across the SVANidhi se Samriddhi Portal. Additional reports in future might be added |
| 4. | Quality Check and Support | - QCI team will do the quality check of profiling done by ULBs - QCI team will also provide on-call support to CLNOs and Nodal officers in terms of any issue regarding SVANidhi se Samriddhi Portal - Quality check parameters are to be automized with the help of IT system to minimize the manual intervention ** |

** Due to enhancement of daily QC, RC manpower will be discussed and increased accordingly and the financial of the same will be on pro-rata basis.

# Methodology:

- Support, maintenance, upgrades, modifications or new releases of the Software Extension to cater to 4500+ ULBs: IT tool has been launched for 3612 ULBs. This proposal will cater to support, maintenance, upgrades, modifications and new releases of the Software Extensions to cater to the launch of Application in total 4500+ ULBs.

The data capturing, monitoring of data, and updating of the status of scheme linkages is done using the web application. A mobile-based application is also provided for the profiling exercise, which enables the capturing of geo-tagged and timestamped photographs and other responses. Mobile app is also provided to the CLNOs for scheme linkage. The components of the IT tool w.r.t stakeholders are listed below: -

  - OTP Verification: On selecting a new form an OTP is generated on vendor’s mobile number or on their alternative number that can be added in case the fetched mobile number is not in use, and the form can only be filled post verification of the OTP.

  - Quality Check and Flagging of Profiled Forms: After successful completion of the assessment, the form is submitted and the status of the form changes to QC Pending. Quality check parameters are to be automized with the help of IT system to minimize the manual intervention. Form is flagged by QCI team in case any errors/ discrepancies are found. After the corrections are made, form is resubmitted by the data enumerator the record moves to QC Pending stage and the form will be rechecked by QCI team.

  - State Admin: QCI has provided each state with a unique ID and a password to sign-in on the portal on their email ids as provided by MoHUA. The State Admins can monitor the progress of each ULB under their state i.e., profiling conducted in the ULB, scheme linkages, users created, and scheme-wise data for both state and city levels. State Admins can also manage users (ULB Admin and Enumerators) of their respective state.

  - ULB Admin: Each ULB admin will be provided a unique ID and password by QCI to sign-in on the portal. The role of ULB admins is to create login IDs for data enumerators. Apart from this, the ULB admin is also responsible for monitoring the progress at the ULB level i.e., profiling conducted in the ULB, scheme linkages, users created, scheme-wise data, flagged forms etc.

  - ULB Official/Data Enumerator: The data enumerators will use the web or mobile application for profiling the vendor and their family members. After logging in to the portal they are able to see vendor’s form along with a few pre-filled data, which is integrated through API linkages. Profiling starts with OTP verification. Once the data is captured for a beneficiary, the data enumerator will be able to see the tentative scheme(s) that the target beneficiary is eligible for, further the form will be checked by QCI Team for quality check, and once approved, the SMS will be sent to the vendor for their eligible scheme.

  - CLNOs: Central schemes that are part of the programme have designated departments. These departments have City Level Nodal Officers i.e., each city has 5 city level nodal officers. The ID and passwords will be provided at CLNO admin-level giving them a feature of creating login id for their city level nodal officers. The portal enables them to update the status of scheme linkages of the beneficiaries on the portal i.e., once a beneficiary is eligible for a certain scheme, they change the status to ‘Applied’, and further they can ‘Sanction’ the application or ‘Reject’ the application by physically authenticating the documents of the beneficiaries.

  - Nodal Officer Central/State: The IDs are provided to the Central and State Level Nodal officers for monitoring the scheme linkages on the Portal.

  - MoHUA Admin: The admin can monitor the progress made at ULB, State, and at Pan India level

w.r.t profiling and scheme linkages.

  - Reporting and Data export: Various reports and data export options in utilities will be provided in the portal to aid the stakeholders in data analysis and monitoring of profiling and scheme linkages for various ULBs. Additional Reporting formats provided by MoHUA to be added for exports across Logins.

  - Scheme linkage Camp Status: Under this feature ULB admins can update the geo-tag location of the camp and capture the photographs of the camp site.

- Dashboards and Analytics: Custom Dashboards have been created for public users and also for other stakeholders of the system like ULB Admin, State Admin and MoHUA Admin. Dashboards provide visual presentation of statistics derived from various parameters for 8 central schemes. Along with this, custom reports and export will also be added in the system as per formats and specifications shared by Ministry.

An analytical BI tool (if required in addition to custom reports) will be provided in the project that will be useful to conduct detailed analytics on different parameters of the application. This will be provided to limited users (Only MoHUA and QCI). Along with this, custom dashboards for public users will be created for the visual presentation of statistics derived from various parameters for 8 central schemes.

- Training: ULB admins and CLNOs of different departments will be trained on how to use the technology platform for profiling and scheme linkages. An online training (via video conference) will be conducted by QCI in which hands-on training will be provided to the stakeholders along with other mediums like training presentations, training videos, user manuals, etc. which will be utilized for subject knowledge.

- Data collection: Prefilled fields from SVANidhi database are being derived through APIs. The mode of capturing data (door to door or calling the beneficiaries one by one) will be as per the discretion of ULB and MoHUA. QCI Team (RC) shall provide assistance as required during the profiling and scheme linkages.

- Analysis and Report: QCI will analyse the data and submit a summary report on a monthly basis till March, 2026 and later a final report capturing the insights at the end of the project duration. Day to day analysis such as camp status, profiling status, and scheme related etc. as per the requirement.

# Project Timeline

| Project Timeline (Extension) (April'25 – March’26) |  |  |
| --- | --- | --- |
| S.No | Components | Time period |
| 1. | Support, maintenance, upgrades modifications or new releases of software Extension | April'25-Mar’26 |
| 2. | Data exports, Reports and Analytics | April'25-Mar’26 |
| 3. | Virtual connect: Regional Coordinator Team (continues process…) and Quality check | April'25-Mar’26 |
| 4. | Project and Support/Maintenance Management | April'25-Mar’26 |
| 5. | Project Handover | Feb’26-Mar’26 |

The project timelines are indicative and are subject to change as per the date of the award of work order. Current Resources will be continuing after the issuance of the work order.

Any major changes in the application will be treated as change request. Costing and timelines of the same will be mutually discussed between QCI and MoHUA and agreed upon. The major changes involve a significant amount of preparation and work with complex situations or major expenses. E.g.: Development of new application or dashboard or implementation of new questionnaire.

# Project Management Unit (PMU)

The project management unit (PMU) will consist of 3 members that will be stationed at MoHUA, Delhi, during the duration of the project. The team leader (QCI) will directly report to Joint Secretary & Director (PM-SVANidhi) and the project coordinatorss will report directly to the team lead (QCI). PMU work includes:

- To coordinate with MoHUA regarding technical and operational issues, the status of profiling of beneficiaries, camp-related concerns, etc.

- Providing data analytics support/reports for the data captured on SVANidhi se Samriddhi portal.

- Review and consolidation of state-level reports and prepare national-level progress reports

- Regular coordination with regional coordinators and overviewing the work done by them on the daily basis

- Preparation of review PPT, daily camp report, query resolution of stakeholders etc.

# Regional/ State Coordinator + Quality Check + Trainer

Regional Coordinators (RCs) are one of the key contributors, they serve as a link between the field (CLNOs and ULB admins) and PMU.

- RCs will conduct the quality check of the profiled forms through different parameters such as, photo, DOB, name, etc.

- Responding & resolving to ULB admins' and CLNOs' inquiries (such as portal related queries, login queries, tech issues, schemes related queries, camp queries, etc.)

- Creating and distributing login ids to stakeholders, as well as ensuring that all associates have their login credentials for profiling and scheme linkage purposes

- Calling the ULBs where the profiled beneficiaries are less in numbers, scheme linkage is low and any query related to quality check of the form

- Calling the CLNOs during the camps to encourage them to link eligible beneficiaries and update the same on the portal

- Analysing and providing the data for monthly report of scheme linkage and profiling

- Functional testing of web and mobile application (such as hard checks, new built features, etc.)

- Refresher training will be given by RC to the assigned states as per the requirement

- Drafting of training schedule and training calendar in consultation with MoHUA

- Modifying the training modules and other training materials

- Creating dummy test login ids for hands on training sessions

- Prepare and impart TTT Model

- Provide hands on tech training to ULB Admins and CLNOs

- Direct any IT related suggestion that may arise during sessions to tech facilitator

- Communicating training requests and providing training to the State/ULBs

Note: Any changes in resources will be made with prior consent and approval of MoHUA

# IT Team & Infra Components

IT team will cater to support, maintenance, upgrades, modifications and new releases of the software extensions. Along with this, infrastructure management team is planned to monitor the parameters of deployed infrastructure to ensure uptime of platform.

## Solution Architecture, improvisations and reviews

Provisioning of a Senior Technical Specialist is being done in the project to design, evaluate, and review any technical changes in the platform and suggest suitable solution for the same.

- Also caters to any performance issues which can arise to cater to data profiling of 70-80 Lakh beneficiaries done by ULB users

- Guide and review the work done by team members

- Infrastructure designing and planning in case of load increase or decrease requirements

## Project Management of Software application components

Project Management of SW component of project including:

- Understanding of specifications of any requested changes and ULB requirements,

- Ensure uptime of platform

- Coordination with various teams - SW, IT and AWS to ensure uptime.

- Monitoring of SW deliveries of the platform.

- Coordination with other stakeholders

- Creation of real time linkage between business and IT team to deliver the requirements within timeline

## Application Support/Improvisations /Query handling/Enhancements to cater to stakeholder needs

- Application support work/improvisations and Enhancements in the application done post application launch.

- Handling of technical queries

- Implementation of minor enhancements as per stakeholder’s feedback

- Data handling and corrections

- New Schemes Implementation

- Frontend, Backend developer, android developer will be planned to cater to above requirements

## Data Export/Analytics support

- Data dumps and Exports as per evolving client requirements

- Implementation of Data Dump tools features

- Data to be provided for complex queries on continuous basis as per Ministry queries

- Required data analysis on large data basis

## Testing Support

- Implementation of UAT and System testing

- Coordination and execution of performance and security testing

- Creation of different test cases in case of any new development requirement or modification in the IT tool

- UAT testing before any new module is released

## IT Infrastructure Support

- Monitoring of IT Infrastructure deployed for Samriddhi project and notify the project team for any discrepancies

- Coordination with AWS team for any additional infrastructure requirements

- Cost optimisation of platform by managing server load in case of increased/reduced requirements

- The work includes, Daily monitoring & analysing data back-up, analysing the user load using load testing tool on regular basis and manage the sizing of the server accordingly, Troubleshooting the system in case of any problem occurs during live project,

- Facilitate the process on technology integration for example SMS feature integration, Work with Regional coordinators to help them provide quality support and,

- Knowledge transfer at the end of the project from the technology vendor as per the requirements

## AWS Support

Project is planned to be deployed on AWS infrastructure. Some support hours are planned with AWS team for any evaluation of new infra technologies and then setup of those.

Discussion/resolution of any unforeseen issues in the platform which results in downtime.

## IT Team Man-Days

IT team for 12 months: April 2025 to March 2026

| S No. | Component |  | Man-Days per Month |
| --- | --- | --- | --- |
| 1. | Solution Architecture, improvisations and reviews |  | 5 |
| 2. | Project Management of Software application components |  | 5 |
| 3. | SW Development team to cater to Application Support/Improvisations /Query handling/Upgrades to cater to stakeholder needs | Frontend | 10 |
| 4. |  | Backend | 10 |
| 5. |  | Android Developer | 10 |
| 6. | Data Exports, Custom Reports |  | 15 |
| 7. | Testing Support |  | 7 |
| 8. | Infrastructure Support |  | 10 |
|  | Total (Days) |  | 72 |

Note: All IT resources allocated in the project will be stationed offsite. While the IT project management resource will be available on calls and physical meetings whenever required.

Allocated IT team will cater to support, maintenance, upgrades, modifications and new releases of the software extensions. This team will ensure the profiling work across the ULBs works seamlessly using the technology platform and also caters to technical queries and issues faced by the stakeholders.

Software extensions will be rolled out based on the feedback/requirements raised by Ministry in periodic meetings. Methodology of implementation of changes will be:

  - Requirements discussion of required change in the software

  - Impact analysis on components and previous data

  - Implementation and Quality Check of changes

  - Release of updated Software on test/staging environment

  - Production release of upgraded Software extension – Production releases will be planned once in a month or at a defined frequency (as per requirement) with collation of work done in that month.

Some of the Software components that will be included as part of the Software upgrades (as & when required & as per approval from MoHUA) are:

- Location information of each record – geocoding of Lat-long

- OTP verification module for Family Editing

- Dashboard changes as per requirements

- Addition of any new central & state level welfare schemes (if required) by the Ministry

- Addition of new Reports as per evolving requirements

- Extract data for custom queries and provide to Analytics team for Analysis

- Custom Dashboards has been created for public users in the Application. Addition of any new component (if required) in custom dashboard.

All the updating/changes/reports extracted in the portal made in the current month should be published on the portal in the first week of next month. Work on the defined tasks in a month will be done on the basis of resource allocation defined above. In case of number of new tasks defined in a month, prioritization of tasks to be done

## SW Technology Stack

| Application Component | Technology |
| --- | --- |
| Front end/ UI | Angular 8 |
| Server Application/API | .Net Core 6.0 |
| RDBMS | PostgreSQL |
| Mobile Application | Android SDK, SQLite |
| Profiling Data Storage | JSON Format |
| Reporting Tools | Big Data Tool (OpenSearch/Apache Spark) |

Details of Estimated Server Infrastructure

| Component | Quantity |
| --- | --- |
| EC2 instances mfd.2xlarge | 5 |
| Load Balancer | 2 |
| Bastion Host for connectivity | 2 |
| RDS PostgreSQL Server | 2 |
| Servers for Load testing | 2 |

### Security Certification of Portal

- QCI will get end to end security testing using empaneled vendor for security testing (As per GIGW)

- The cost of security audit will be charged as per actuals & will be borne by MoHUA.

- Estimated time for security testing and adhering to security compliances will take 2 months approx.

### Backup and Disaster Recovery Plan

- Data backup is taken daily with automated backup scripts

- The team ensures, review and monitor the backups.

- Data backup can be taken on an alternate cloud environment in case disaster recovery is needed. AWS has tie-ups with alternate providers (can be planned if required and this will incur an extra cost which is over and above the proposal)

## SMS and DLT Charges

In order to start the profiling of Street Vendors it is mandatory to enter the OTP received on their registered mobile number. Once the profiled form is approved Vendor is notified about the eligible schemes through SMS. In order to do so in total there are minimum 5 messages sent to the beneficiary i.e., Eligibility SMS in English and regional language for vendor and family and OTP before profiling.

- On an average 7 (Eligibility SMS consists of 9 variables which results in increasing the character count) SMS will be sent to a beneficiary using SMS and DLT services.

- The cost of SMS will be chargeable to MoHUA as per actuals on monthly basis.

- Total estimated cost of SMS and DLT is (13,25,000 * 0.20 * 7): ₹ 18,55,000

# Handover and Knowledge Transfer Plan

QCI shall initiate Exit Management and knowledge Transfer Process 45 days prior to the contract termination date. MoHUA will assign a handover team and will assign a point of contact for hand-over QCI will promptly on the commencement of the exit management period supply to the MoHUA the following:

- All information relating to the project implementation including confidential information pertaining to the beneficiaries of the project;

- Documentation relating to IT Systems – Deployment and Technical Architecture of IT Systems, User and Training Manuals.

The IT infrastructure and other requirements for the migration shall be communicated to MOHUA team well in advance for undertaking necessary arrangements. QCI will initiate the migration of IT system 45 days prior to the termination of contract. QCI shall provide necessary handholding and transition support to designated staff for maintaining the system during this period. The handholding support will include conducting walkthrough demonstration for the IT Infrastructure, handing over all relevant documentation, addressing the queries/clarifications with respect to the working/performance levels of the infrastructure, conducting training sessions of functional usage of application. QCI along with key stakeholders would ensure successful migration of data, IT Infrastructure and related application, etc., before termination of the contract.

Project Handover to be completed within 45 Days. Ministry has to provide same environment to transfer the technology/infra. Migration cost should be borne by QCI. Hardware and Software for the same will be provided by MoHUA.

# Manpower and Commercial

Financials (For 12 months): April 2025 to March 2026

| Duration: April 2025 to March 2026 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Category | Sub Category | Units | Unit Cost (in INR) | Man- months | Total (in INR) |
| QCI Professional | Project Lead | 1 | ₹ 1,56,800 | 12 | ₹ 18,81,600 |
|  | Operation Coordinators | 2 | ₹ 1,06,400 | 12 | ₹ 25,53,600 |
|  | Regional Coordinators + Quality Check Team + Trainers | 3 | ₹ 78,400 | 12 | ₹ 28,22,400 |
| Technology Cost (Portal, Dashboard & Mobile Application) | IT-tool Maintenance, Support and AWS Business Support | - | ₹ 5,00,000 | 12 | ₹ 60,00,000 |
| Sub-total Cost |  |  |  |  | ₹ 1,32,57,600 |
| Admin Cost | 12% |  |  |  | ₹ 15,90,912 |
| Total Cost (A) |  |  |  |  | ₹ 1,48,48,512 |

| Cost of components mentioned below is projected tentatively and are as per Actuals |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SMS and DLT charges** | Budgetary estimate (considering 20 paisa per SMS) @ 7 SMS per beneficiary | 13,25,000 | ₹ 0.20 | 7 (SMS per beneficiary) | ₹ 18,55,000 |
| Server Cost** | Infra Structure Cost | - | ₹ 7,00,000 | 12 | ₹ 84,00,000 |
| Total Cost (B) |  |  |  |  | ₹ 1,02,55,000 |

| Grand Total Cost (Excluding GST) A+ B | ₹ 2,51,03,512 |
| --- | --- |

**These costs will be as per actuals and subject to change as per the usage of the functionality or product.

Terms of Payment

The payment structure will be as follows:

- Quarterly Payment details for the period April 2025 to March 2026 is attached in Annexure 1.

- The cost head of invoices will be based on QCI resources, monthly technology cost and admin cost.

- Infrastructure (Server) cost and SMS charges will as per the actual usage.

- Cost mentioned in commercials are exclusive of GST*.

- During the project, in case there is a change in methodology which would result in a change in manpower, then it might incur extra cost.

- Any further changes or modification in terms of usage or 3rd party functionality integration as per approval from MoHUA will result in additional cost as per the actuals (License / Subscription Cost).

- Any major changes in the application will be treated as change request. Costing of the same will be mutually discussed between QCI and MoHUA and agreed upon.

- In case of any requirements, where manpower will be increased. Cost will be charged in pro rata basis.

- Any support required from ministry is as per previous proposal.

# Annexure 1

| Duration: April 2025 to March 2026 |  |  |  |
| --- | --- | --- | --- |
| Quarter | Months | Components | Amount to be disbursed |
| Quarter 1 | April'25 - June'25 | QCI Professional Cost | ₹ 18,14,400 |
|  |  | Technology Cost | ₹ 15,00,000 |
|  |  | Sub-Total | ₹ 33,14,400 |
|  |  | Admin (12%) | ₹ 3,97,728 |
|  |  | Total | ₹ 37,12,128 |
| Quarter 2 | July'25 - Sept'25 | QCI Professional Cost | ₹ 18,14,400 |
|  |  | Technology Cost | ₹ 15,00,000 |
|  |  | Sub-Total | ₹ 33,14,400 |
|  |  | Admin (12%) | ₹ 3,97,728 |
|  |  | Total | ₹ 37,12,128 |
| Quarter 3 | Oct'25 - Dec'25 | QCI Professional Cost | ₹ 18,14,400 |
|  |  | Technology Cost | ₹ 15,00,000 |
|  |  | Sub-Total | ₹ 33,14,400 |
|  |  | Admin (12%) | ₹ 3,97,728 |
|  |  | Total | ₹ 37,12,128 |
| Quarter 4 | Jan'26 - Mar'26 | QCI Professional Cost | ₹ 18,14,400 |
|  |  | Technology Cost | ₹ 15,00,000 |
|  |  | Sub-Total | ₹ 33,14,400 |
|  |  | Admin (12%) | ₹ 3,97,728 |
|  |  | Total | ₹ 37,12,128 |

| Duration: April 2025 to March 2026 |  |  |  |
| --- | --- | --- | --- |
| Cost of components mentioned below is projected tentatively |  |  |  |
| Quarter | Months | Components | Projected Cost* |
| Quarter 1 | April'25 - June'25 | SMS and DLT charges | ₹ 4,63,750 |
|  |  | Server Cost | ₹ 21,00,000 |
|  |  | Total | ₹ 25,63,750 |
| Quarter 2 | July'25 - Sept'25 | SMS and DLT charges | ₹ 4,63,750 |
|  |  | Server Cost | ₹ 21,00,000 |
|  |  | Total | ₹ 25,63,750 |
| Quarter 3 | Oct'25 - Dec'25 | SMS and DLT charges | ₹ 4,63,750 |
|  |  | Server Cost | ₹ 21,00,000 |
|  |  | Total | ₹ 25,63,750 |
| Quarter 4 | Jan'26 - Mar'26 | SMS and DLT charges | ₹ 4,63,750 |
|  |  | Server Cost | ₹ 21,00,000 |
|  |  | Total | ₹ 25,63,750 |

*These costs will be as per actuals and subject to change as per the usage of the functionality or product. It may increase or decrease as per the usage.

# Annexure 2

| S No. | Role | Qualifications |
| --- | --- | --- |
| 1. | Project Lead | - Education: Masters or Bachelors in any discipline from recognized institute/ universities - Experience: 5+ years’ experience working in Private/Public/PSU - Work experience in Social Sector/ public policy/ monitoring of projects and schemes/industry |
| 2. | Operation Co-ordinator | - Education: Masters or Bachelors in any discipline from recognized institute/ universities - Experience: 3+ years’ experience working in Private/Public/PSU. - Work experience in Social Sector/ public policy/ monitoring of projects and schemes etc. - Support research, analysis and problem solving using a variety of tools and technique |
| 3. | Regional/ State Co-ordinator | - Education: Bachelors in any discipline from UGC recognized institute/ universities - Experience: Minimum 1 year of work experience. (Most preferably government/ public policy sector) |