National Horticulture Board

Third-Party Evaluation of Scheme-1: Development of Commercial Horticulture, and Scheme-2: Capital Investment Subsidy for Cold Storage including storages for horticulture products, under National Horticulture Board for the FY 2023-24 Project Proposal submitted to: National Horticulture Board, Ministry of Agriculture & Farmers Welfare, Government of India

Quality Council of India

An Autonomous Body setup by

Ministry of Commerce and Industry, Govt. of India

2nd Floor, Institution of Engineers Building,

2, Bahadur Shah Zafar Marg,

New Delhi – 110002 | Ph: +91-11-2337 9321

E-mail: hari@qcin.org

Mobile: 9899015306

Date: 23rd October 2023

(Page intentionally left blank)

# Table of Contents

Table of Contents	iii

LIst of Figures	iv

List of Tables	v

1.	INTRODUCTION	6

1.1.	National Horticulture Board	6

1.2.	Aims & Objectives of NHB Schemes	6

2.	ABOUT QUALITY COUNCIL OF INDIA	7

3.	SCOPE AND OBJECTIVE of Third party Evaluation	8

3.1.	Scope of Work	8

3.2.	Objectives	8

4.	METHODOLOGY AND IMPLEMENTATION	9

4.1	Secondary Research and Preliminary Analysis	9

4.2	Development of Framework	9

4.3	Training & Deployment of Assessors	11

4.4	Data Quality Check	11

4.5	Data Analysis	12

4.6	Reports	12

5.	Project Timeline	13

6.	Financials & Payment Milestone	14

7.	GENERAL TERMS	15

8.	QCI PAST EXPERIENCE	16

9.	Curriculum Vitae of the Key Personnel	22

# LIst of Figures

Figure 1: Glimpse of a tech platform indicating the process of data collection and quality check	12

Figure 2: Proposed Timeline of the Project	13

# List of Tables

Table 1: Proposed Sample Size	11

Table 2: Deliverables linked to Project Timeline	13

Table 4: Proposed Project Financial	14

Table 5: Payment Milestones	14

# INTRODUCTION

## National Horticulture Board

  - The National Horticulture Board (NHB) was set up by the Government of India in 1984 as an Autonomous organization under the administrative control of Ministry of Agriculture and Farmers Welfare and registered as a society under Societies Registration Act with its headquarters at Gurugram, Haryana.

  - The broad aims and objectives of the Board are to develop production clusters/hubs for integrated Hi-tech commercial horticulture, development of post-harvest and cold chain infrastructure, ensuring availability of quality planting material and to promote adoption of new technologies/tools/ techniques for Hi-tech commercial horticulture etc.

## Aims & Objectives of NHB Schemes

The main objectives of the NHB are to improve integrated development of the Horticulture industry and to help in coordinating, sustaining the production and processing of fruits and vegetables. Detailed objectives of the Board are as under: -

  - Development of hi-tech commercial horticulture in identified belts and make such areas vibrant with horticultural activity, which in turn will act as hubs for development of horticulture.

  - Development of modern post-harvest management infrastructure as an integral part of area expansion projects or as common facility for cluster of projects. Development of integrated, energy efficient cold chain infrastructure for fresh horticulture produces.

  - Popularization of identified new technologies / tools / techniques for commercialization / adoption, after carrying out technology and need assessment.

  - Assistance in securing availability of quality planting material by promoting setting up of scion and root stock banks / mother plant nurseries and carrying out accreditation / rating of horticulture nurseries and need based imports of planting material. Promotion and market development of fresh horticulture produce.

  - Promotion of field trials of newly developed/imported planting materials and other farm inputs; production technology; PHM protocols, INM and IPM protocols and promotion of applied R&D programs for commercialization of proven technology.

  - Promotion of Farm Mechanization in Horticulture through demonstration and its uses at farmers’ field level to reduce labor cost and increase the productivity of Horticulture crops. Promotion of applied R & D for standardizing PHM protocols, prescribing critical storage conditions for fresh horticulture produce, bench marking of technical standards for cold chain infrastructure etc.

  - Transfer of technology to producers/farmers and service providers such as gardeners, nurserymen, farm level skilled workers, operators in cold storages, work force carrying out post-harvest management including processing of fresh horticulture produce and to the master trainers.

  - Promotion of consumption of horticulture produce and products. Promoting long distance transport solution for bulk movement of horticulture produce through rail etc.

# ABOUT QUALITY COUNCIL OF INDIA

  - The Quality Council of India (QCI) has been set up as a non-profit autonomous society registered under Societies Registration Act XXI of 1860 to establish an accreditation structure in the country and to spread quality movement in India by undertaking a National Quality Campaign.

  - QCI was established as an autonomous non-profit organization by the Government of India together with the Indian Industry represented by the three major industry associations: ASSOCHAM, Cll and FICCI. The Department for Promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry is the nodal point for all matters connected to quality and QCI.

  - The Council was established to create a mechanism for third party assessment of products, services and processes. In tune with the international best practices, it was envisaged that the Council will ensure that the quality of life of citizens is improved. It was therefore befitting that the Council was organized as an Independent Professional body with representation from the government and industry, and with its own rules, powers and functions strictly as per the MoA of the Society.

  - The National Accreditation Board for Certification Bodies (NABCB), a constituent Board of QCI, is the apex national accreditation body which provides accreditation to Certification as well as Assessment Bodies in accordance with ISO Standards, international requirements / guidelines and NABCB Accreditation Criteria.

  - NABCB is internationally recognized and represents the interests of the Indian industry at international cooperation frameworks such as the International Accreditation Forum (IAF), International Laboratory Accreditation Cooperation (ILAC) and its recognized regional bodies such as the Asia Pacific Accreditation Cooperation (APAC). Its objective is to promote acceptance of India’s certifications and inspections internationally by becoming a signatory to the Multilateral/Mutual Recognition Arrangements (MLAs/MRAs) of these bodies after undergoing successful international peer evaluations.

  - The National Accreditation Board for Testing and Calibration Laboratories (NABL) is another constituent board of QCI that accredits laboratories across scopes. NABL is a Mutual Recognition Arrangement (MRA) signatory member of Asia Pacific Accreditation Cooperation (APAC) and International Laboratory Accreditation Cooperation (ILAC) since 2000. NABL in the year 2016 achieved the APAC MRA signatory status for Proficiency Testing Providers (PTP) and Reference Material Producers (RMP) schemes along with extension in the existing fields of Testing, Calibration and Medical till December 2020. In October 2019, NABL has also obtained ILAC MRA for Proficiency Testing Providers (PTP) accreditation program (ISO/IEC 17043) in addition to existing Testing including Medical (ISO/IEC 17025 and ISO 15189) and Calibration (ISO/IEC 17025) programs.

# SCOPE AND OBJECTIVE of Third party Evaluation

## Scope of Work

In accordance with the aims and objectives of the schemes of National Horticulture Board, QCI proposes to conduct a Pan-India Third Party Evaluation of the two Schemes under National Horticulture Board for the annual years 2023-2024, with scope of work as mentioned below:

  - Scheme-1: Development of Commercial Horticulture through Production and Post-Harvest Management of Horticulture Crops, which covers:

- Assessment of Commercial Horticulture Development in open field scheme.

- Assessment of Commercial Horticulture Development in protected cover scheme.

- Assessment of Integrated Post Harvest Management schemes.

  - Scheme-2: Capital Investment Subsidy Scheme for Construction / Expansion / Modernization of Cold Storages and Storages for Horticulture Products, which includes:

- Verification of Civil structure of the cold storage units.

- Verification of Mechanical components of the cold storage units.

- Assessment of current functionality, suitability and capacity of the cold storage units.

*The Third Party Evaluation will follow the prescribed guidelines of the schemes.

## Objectives

The overarching objective of the study are as follows:

- To understand the outreach of the horticulture activities across the country.

- To document the good practices adopted in development of horticulture schemes by NHB.

- Verification of process of planting material procurement procedure and related documents.

- To assess the usefulness of the technological mechanizations used for production, post-harvest management and primary processing of the horticultural crops.

- To evaluate and assess the capacity utilization of the cold storage units.

- To assess the process of implementation of the schemes as per the guidelines.

- To gauge the usage of the subsidy facilitated for each component of the schemes.

- To assess the intangible socioeconomic impact of the programme on its beneficiaries.

- To understand the impact of cold storage units in the development of horticulture markets.

- Consultation with stakeholder regarding scheme implementation, its components and other necessary upgradation if required during the assessment.

# METHODOLOGY AND IMPLEMENTATION

## Secondary Research and Preliminary Analysis

The data for the baseline information was gathered during the 2010-2022 phase and the authentic source available in public domain i.e., NHB website, which became the basis for the secondary research and analysis at the very initial stage of the preparation of project proposal. The primary motive of conducting the secondary research was to build an understanding of the Schemes for the development of commercial horticulture. QCI undertook the secondary research through the guidelines of NHB Schemes, and with expert advice and guidance of the senior officials of QCI. Documents and resources available on the website were studied along with the data and a draft work plan is prepared.

QCI will require a data set concerning the major stakeholders, especially the data of individual beneficiaries provided by the NHB to study for further preliminary analysis of the project for the purpose to:

- Understand the coverage of the horticulture scheme in the country.

- Identify the range of subsidy provided for different initiatives/projects.

- Prepare a systematic work plan for the evaluation study including methodology, timeline and proposal of the assessment team.

- Carry out the Third Party Evaluation of the two schemes of National Horticulture Board.

## Development of Framework

In continuation of Third-Party Evaluation of projects sanctioned by NHB in FY 2019-20 to 2022-23, for the FY 2023-24, QCI will develop a robust framework for the evaluation study. The framework includes the identification of stakeholders, development of the questionnaire, development of data collection tools, conducting a pilot study, and determination of sample size and site assessment.

- Identification of Stakeholders

Stakeholders are the people, group or organization involved in the implementation of a scheme or programme. It includes the targeted beneficiaries, implementation agency, financial institutions, industries and other groups/ individuals/ organization impacted from the programme. It is crucial for an effective study to consider and study the viewpoints of all the stakeholders involved in the scheme. On the basis of secondary research, some of the major stakeholders identified for interaction and assessment are mentioned as below:

    - Beneficiary farmers

    - National Horticulture Board official at selected states and HQ.

    - NHB accredited nursery distribution of plants, equipment, and raw material as per NHB guidelines.

    - Banks and Financial Institutions

- Development of the questionnaire

QCI will develop an assessment questionnaire to interact with the beneficiaries and stakeholders of the study taking into account the goals and objectives of the National Horticulture Board & its schemes studying which the scope of the evaluation study was prepared with mutual discussion with NHB. The questionnaire will aim to capture the information about basic details, about the availed facilities under the schemes, socio-economic impact of the schemes, related information about the projects and its related documents, etc. as per the standards and procedures mentioned in the guidelines of the schemes.

- Development of data collection tools

The questionnaire will be supported by web supported data collection tools such as, mobile application monitored and advanced with the backend support by the QCI team at the headquarters, which will help in collecting the responses and information on field and simultaneous quality check at the QCI headquarters.

- Pilot study

After the development of questionnaire and data collection tools, a Pilot study of the project will be conducted to check the effectiveness of the questionnaire and the data collection tools which will be used for the data collection during the assessment of the program. The learnings and observations from the pilot study will be shared with the NHB for inputs and validation. It will be helpful to address the challenges, resolve the bottlenecks, and make the data collection process smooth and seamless. The inputs and recommendations from NHB will be further incorporated in the designed framework of the evaluation study.

- Determination of sample size

A sample size of a study is the representative population of the set of people who are part of the program. The sampling method chosen for the evaluation study is stratified-random sampling method. On the basis of the data gathered from National Horticulture Board official website, the sample size of the beneficiary was stratified considering, geographical location of the farm land, horticultural crop for which the type of scheme subsidy was availed, gender of the beneficiary, caste of the beneficiary, and others. The whole project of NHB is distributed among Scheme I (with further 5 sub-schemes) & Scheme II (for Cold Storage establishment). So sample size is also calculated based on 95% Confidence Level (Cl) & 5% Margin of Error (MoE) for both schemes separately and further distributed according among sub-schemes as per their ratio to the population.

Scheme I: In continuation of Third-Party Evaluation of projects sanctioned by NHB in FY 2019-20 to 2022-23, for the FY 2023-24 approximate number of projects supported under Scheme-I will be 1000. In addition to previous sampling of 285, QCI proposes additional 10% of the sanctioned project for the year. Approximate Sample from FY 2023-24 will be 100. Samples will be distributed among “Open Field Cultivation, Protected Cultivation, PHM, Primary Processing Units, & Others” categories. Further, the Stratified Sampling approach will be applied to select the individual farms.

Scheme II: In continuation of Third-Party Evaluation of projects sanctioned by NHB in FY 2019-20 to 2022-23, for the FY 2023-24 approximate number of projects supported under Scheme-II will be 80 to 100. In addition to previous (Projects sanctioned in FY 2010-20 to 2022-23) sampling of 96 based on 95% Confidence Level & 5% Margin of Error, QCI proposes additional 10% of the sanctioned project for the year. Approximate Sample from FY 2023-24 will be 8 to 10. Stratified Sampling will be applied for the selection of each cold storage under Scheme-II.

The proposed sample size of the study is as follows:

Table 1: Proposed Sample Size

| Schemes | Total Population | Sample size (10% of Sanctioned Projects) | Population component |
| --- | --- | --- | --- |
| Scheme I | 900 (Approx.) | 90 | 1. Open Field Cultivation, 2. Protected Cultivation, 3. PHM, 4. Primary Processing Units, & 5. Others |
| Scheme II | 80 to 100 (Approx.) | 8 to 10 | - Cold Storage establishment |

Alongside above mentioned sample of beneficiaries, other stakeholders including the representatives/ officials of NHB, industries and the banks & financial institutions will also be interacted for the all-round understanding of the scheme.

## Training & Deployment of Assessors

In continuation of Third-Party Evaluation of projects sanctioned by NHB in FY 2019-20 to 2022-23, for the FY 2023-24 a team of experts including senior assessors from QCI will be trained extensively for the on-ground/ physical assessment of the evaluation study. The training will equip the assessment team with knowledge, enhance their understanding about the scheme, and the evaluation study which will make them capable to carry out the assessment in an efficient manner.

After the training, the on-ground/ physical assessment team will be deployed at their planned and assigned locations for the data collection & assessment of the schemes. The on-ground/ physical assessment will be supported & monitored by the professional team at the QCI headquarters with the help of a web supported portal managed from the backend.

## On-Field Assessment

In continuous of QCI’s Third Party Evaluation of Scheme-I & II of NHB for FY 2019-20 to 2022-23, on-field assessment of the sanctioned projects in the FY 2023-24 will be executed in two phases.

- During 1st phase, the projects sanctioned till October 2023 will be evaluated in Nov to Dec 2023.

- During 2nd Phase, the projects sanctioned during Nov 2023 to March 2024, the on-field evaluation will be executed in end of March & starting April of 2024.

The process of data collection will be conducted using a Computer Assisted Personal Interview (CAPI) or Mobile based Applications/Platform that will capture geo-tagged and time-stamped photographs and responses for a transparent, accurate, and speedy process. As mentioned above, Interaction and Interviews with the stakeholders shall be facilitated by inspectors/auditors/field-enumerators. A comprehensive data framework will be created in order to analyze data according to all target parameters. Field assessments will include a mix of quantitative and qualitative, descriptive questions. All interviews & interactions shall be documented in a format as specified for analysis and keeping record.

## Data Quality Check

A dedicated team of professionals was deployed at the QCI headquarters to monitor and provide support to the on-ground team of assessors. The collected data will be checked in real time by the QCI Professional at the backend and will be further re-checked at multiple levels by the experienced Quality check professionals to eliminate the margin of error and maintain the quality and authenticity of the data.

Figure 1: Glimpse of a tech platform indicating the process of data collection and quality check

During the on-ground/ physical assessment, a team of senior QCI professionals will visit the locations for monitoring and providing the required support where the assessors will be deployed for assessment.

## Data Analysis

The information collected by the assessment team considering the data and information gathered from all the identified stakeholders of the study will be analysed and an in-depth analysis of each aspect of the schemes will be taken into consideration for the evaluation study. The quantitative and qualitative analysis will be presented followed by the Observations derived from the third party evaluation.

## Reports

Inception cum Pilot Report: A framework developed by the QCI for the evaluation study for the projects sanctioned by NHB during FY 2019-20 to 2022-23, will be considered as the inception & pilot for the projects for the FY 2023-24 as well.

At the initial stage of the on-ground/ physical assessment, the Inception report of the project will be shared with the NHB. The inception report will consist of preliminary analysis of the assessment data & information, framework and questionnaire, data collection tools, observations from the pilot study, initial status update of the on-ground/ physical assessment, probable constraints and challenges, plan of action ahead and tentative project timeline of the evaluation study.

Status Update during On-Filed Assessment: On completion of 50% by Dec 2023 & 100% by April 2024 of the on-field assessment, QCI will share status update report to NHB.

Draft & Final Report: The whole information and data collected during the assessment will be cleaned at levels of quality checks and will be submitted to the National Horticulture Board along with the draft report for their feedback, suggestions and recommendations. After incorporating the feedbacks, suggestions and recommendations received from the NHB, the final report of the evaluation study along with the required data will be submitted to the NHB for consideration.

# Project Timeline

In continuous of QCI’s Third Party Evaluation of Scheme I & II of NHB for FY 2019-20 to 2022-23, assessment of the sanctioned projects in the FY 2023-24 from both schemes is proposed to be completed within 6 months* from the date of issue of both work orders as per the below schedule. The proposed timeline will be in phases.

- During 1st phase, the projects sanctioned till October 2023 will be evaluated in Nov to Dec 2023.

- During 2nd Phase, the projects sanctioned during Nov 2023 to March 2024, the on-field evaluation will be executed in end of March & starting April of 2024.

Project Assessment Timeline –

Table 2: Deliverables linked to Project Timeline

| Activity | Duration | Deliverable |
| --- | --- | --- |
| Conceptualization & Evaluation Planning | 2 Weeks from Work Order | Draft Assessment Framework |
| Pilot Study | Within 4 Weeks of Work Order | Pilot cum Inception Report |
| Evaluation of Scheme-I & II of NHB for FY 2019-2024 | 4 Months after Pilot | Status Update at mid & completion of On-Field Assessment |
| 1st Phase of Evaluation | Within 2 Months of WO |  |
| 2nd Phase of Evaluation | Within 5.5 Months of WO |  |
| Data Analysis & Report Writing | 5.5 Months of WO | Draft Report |
| Final Report | Within 6 Months of WO | Final Report |

Figure 2: Proposed Timeline of the Project

* The timeline is subject to change due to any unforeseen circumstances.

# Financials & Payment Milestone

In continuous of QCI’s Third Party Evaluation of Scheme-I & II of NHB for FY 2019-20 to 2022-23, financials for the assessment of the sanctioned projects in the FY 2023-24 as follows,

Sl. No.; Activity; Total Cost. 1; Professional & Quality Control Cost; ₹ 6,50,000.00. 2; Assessment Cost. 2.1; Assessment of Scheme- I (10% of sanctioned projects under scheme I); ₹ 7,60,136.00. 2.2; Assessment of Scheme- II 10% of sanctioned projects under scheme II); ₹ 1,28,189.00. 3; Technology, IT Infrastructure, & Reporting Cost; ₹ 1,00,000.00. QCI Admin Cost @12%; ₹ 1,96,599.00. Total Project Cost; ₹ 18,34,924.00* + Applicable Taxes.

*This amount is exclusive of any taxes and levies. *The above rates are applicable for current year, for coming years there shall be an increase of 8% every year to meet out the inflation. or subject to review after one year.

Table 3: Proposed Project Financial

| Payment Structure Linked to Milestones |  |  |
| --- | --- | --- |
| Milestones | Stages | Amount to be disbursed |
| Milestone 1 | After completion of 50% of On-Field Assessment for phase I and Phase II | 50% |
| Milestone 2 | On Final Submission of Assessment Report for phase I and Phase II | 50% |

Table 4: Payment Milestones

# GENERAL TERMS

- AMENDMENT OF AGREEMENT: No amendment or modification of the agreement authorising this project shall be valid unless it is made in writing jointly by both parties or by their authorized representatives and specially stating the reason for amendment to this agreement. The modification/changes shall be effective from the date of which they are made/executed unless otherwise agreed to.

- FORCE MAJEURE: The parties shall ensure due compliance with the terms of this agreement. However, no party shall be liable for any claim for any loss or damage whatsoever arising out of failure to carry out the terms of the agreement to the extent such a failure is due to force majeure events such as fire, rebellion, mutiny, civil commotion, riots, strike, lockout, force of nature, accident, act of God, or any other reason beyond the control of concerned party.

- ARBITRATION: The disputes, if arising, shall be settled by arbitration with sole arbitrator (to be jointly appointed in 30 days) in accordance with the procedure prescribed in the Indian Arbitration and Conciliation Act, 1996 or any statutory modification or re-enactment thereof and the rules made thereunder and for the time being in force. Proceedings shall, unless otherwise agreed by the parties, to be held in Delhi, India. Governing law will be laws of India. Language will be English.

- NOTICE: All notices permitted or required to be given under the provisions of this agreement shall be deemed to be sufficiently given if written and delivered personally or sent to the other party by telefax or certified or registered air mail or email and addressed to the registered office of the other party as follows or to such other party address as the party may give notice in writing. Unless otherwise provided herein all such notices shall be deemed to have been given as of the date they are personally delivered or transmitted by telefax or email or deposited in the mail.

- TERMINATION OF AGREEMENT: Either party shall have the right to terminate the agreement at any time by giving thirty days’ notice in writing in advance indicating reasons for same to the other party. The reasons however, will need to be justified and in case the termination leads to delay/pause/abortion of the project, the Authority reserves the right to not make any payments further to the date of project termination as indicated by either party.

# QCI PAST EXPERIENCE

Below are the details of industry related major past projects done by Quality Council of India:

| Sr. No. | Details of Project - 1 |  |
| --- | --- | --- |
|  | Name of the Evaluation Study | Third Party Assessment of FCI Warehouses-reg. |
|  | Name and Address of the Organization | Food Corporation of India, 16-20, Barakhamba Road, New Delhi – 110001 |
|  | Total Survey Cost (INR) | Rs. 2,39,89,840/- |
|  | Work Order/ Agreement No. and date | No. E.1(1)/QCI/2021/Stg VIII and 12.08.2021 |
|  | Brief Description of the Survey/Study | QCI worked to design, develop and deploy interventions in the supply chain of food grains paid for by the government with an aim to: - review and upgrade existing standards and practices; - bring end-to-end digitization and traceability; - strengthen the quality management in systems and processes to make the entire procurement and distribution system much more transparent, technology driven and user-friendly for the stakeholders with continuous and sustained monitoring. |

| Sr. No. | Details of Project - 2 |  |
| --- | --- | --- |
|  | Name of the Evaluation Study | Third Party Assessment of Procurement Centres in KMS 2021-22 and RMS 2011-23-reg. |
|  | Name and Address of the Organization | Food Corporation of India, 16-20, Barakhamba Road, New Delhi – 110001 |
|  | Total Survey Cost (INR) | Rs. 3,68,72,640/- |
|  | Work Order/ Agreement No. and date | No. Proc.I/ 1(1)/ 2021/QCI and 10.12.2021 |
|  | Brief Description of the Survey/Study | QCI conducted the third party assessment in 434 purchase centres as per the state wise list covering both Kharif Marketing Season and Rabi Marketing Season, which covers: - Assessment of Infrastructural Facilities at the Procurement Centres. - Comprehensive Assessment of activities performed in procurement centres vis-à-vis standard operating procedures. - Detailed feedback from farmers and other stakeholders. - Random assessment of quality of grain procured. |

| Sr. No. | Details of Project - 3 |  |
| --- | --- | --- |
|  | Name of the Evaluation Study | Survey, analysis of Pulses & Oilseeds in the State of Rajasthan-reg. |
|  | Name and Address of the Organization | National Agricultural Cooperative Marketing Federation of India (NAFED) Ltd., NAFED House, Siddhartha Enclave, Ashram Chowk, Ring Road, New Delhi – 110014 |
|  | Total Survey Cost (INR) | Rs. 1,28,10,297/- |
|  | Work Order/ Agreement No. and date | HO/PULSES/SURVEYOR/35/2018-19/7593 and 12.10.2018 |
|  | Brief Description of the Survey/Study | QCI conducted the survey, analysis of Pulses, Oilseeds, Groundnut, Moong, Soyabeen and Urad to be procured under Price Support Scheme (PSS) in the state of Rajasthan. |

| Sr. No. | Details of Project - 4 |  |
| --- | --- | --- |
|  | Name of the Evaluation Study | Third Party Verification under Atal Bhujal Yojana (Atal Jal) |
|  | Name and Address of the Organization | Department of Water Resources, River Development and Ganga Rejuvenation, Ministry of Jal Shakti, Government of India, Shram Shakti Bhawan, Rafi Marg, New Delhi – 110001 |
|  | Total Survey Cost (INR) | Rs. 10,31,36,251.68/- |
|  | Work Order/ Agreement No. and date | No T-79011/1/2020-Atal Jal/8-13 and 18th Sept. 2020 |
|  | Brief Description of the Survey/Study | Quality Council of India was engaged for carrying out independent verification of the results of the Atal Bhujal Yojana in respect of Disbursement Linked Indicators (DLIs) listed below: DLI#1 - Public disclosure of ground water data/information and reports DLI#2 - Preparation of Community-led Water Security Plans DLI#3 - Public financing of approved Water Security Plans through convergence of ongoing/new schemes DLI#4 - Adoption of practices for efficient water use DLI#5 - Improvement in the rate of decline of groundwater levels |

| Sr. No. | Details of Project - 5 |  |
| --- | --- | --- |
|  | Name of the Evaluation Study | Quality Assessment of Rural Electrification under Deendayal Upadhyaya Gram Jyoti Yojana (DDUGJY) – regarding. |
|  | Name and Address of the Organization | Ministry of Power, Government of India, Shram Shakti Bhawan, New Delhi – 110001 |
|  | Total Survey Cost (INR) | Rs. 2.71 Crores/- (approx.) |
|  | Work Order/ Agreement No. and date | No. 44/15/2017-RE and 18th September, 2018 |
|  | Brief Description of the Survey/Study | Quality Council of India was engaged to evaluate the quality of the installed infrastructure on ground, its functionality and the quality of services delivered, under the scheme. The twofold objective of the schemes included: - Physical Verification of infrastructure, includes visual inspection of power distribution infrastructure installed in the villages under DDUGJY scheme comprising of distribution transformers, High Tension Line & Poles, and Low Tension Lines and Poles. - Citizen Feedback Survey to gauge the end user perspective and experience of electricity provided in the households and public places. |

| Sr. No. | Details of Project - 6 |  |
| --- | --- | --- |
| 1 | Name of the Evaluation Study | Interim & Final Impact Evaluation of TEQIP-III |
| 2 | Name and Address of the Organisation | National Project Implementation Unit (NPIU) Ministry of Education, Govt. of India Address: 301-302, Plot no.- 9, Jasola Vihar, New Delhi- 110025 |
| 3 | Total survey cost (INR) | Rs. 46,25,600/- |
| 4 | Work Order/ Agreement No. and date | TEQIP III/2019.TPIE/4 and Date: 23rd December 2019 |
| 5 | Brief description of the survey/study | Study assessed the overall impact accrued due to project TEQIP-III in strengthening the quality of engineering education against the pre-defined result framework, such as mapping of institutions status at the joining and completion of project in terms of: NBA accreditation, Transition rate, Share of women and SC/ST students in enrolment, Training of final-year students for exit exam (GATE), Qualifying graduates in exit exam (GATE), Students and faculty satisfaction, Employers satisfaction, Faculty development and training, Publication of research articles, etc.; extent of capacity development along with plan of sustainability in terms of governance as well as academic; impact and achievements of twinning programme. |

# Curriculum Vitae of the Key Personnel

| Name of the Organization | Quality Council of India |
| --- | --- |
| Name of Expert | Dr. Hari Prakash |
| Date of Birth | 26.01.1966 |
| Nationality | Indian |
| Highest Education: | Ph.D. (Horticulture); Expert - Ecology and Environment |
| Membership in Professional Associations | • Pant Nagar Horticulture Society (PNHS), • Agriculture Alumni Association of Pant Nagar (AAAP), • All India Management Association (AIMA), • International Food and Agribusiness Management Association (IFAMA)- US |
| Presentations, Publications & Trainings | • National Conference AMIFOST-2017, Guest of Honor for the Valedictory function, Sept 2017. • Case study presented in Workshop on Strengthening Institutions Offering Productivity Courses held from 16-19 May, 2016, Jakarta, Indonesia conducted by APO, Japan. • EIA scheme presentations at PHD Chamber of Commerce, NEERI, 2014. • Conducted 5 GAP training programmes sponsored by USAID+ Michigan State Univ.2011. • Organic Farming-Opportunities & constraints published in National Horticulture conference Dec, 2010. • Presented Voluntary Certification Scheme for Medicinal Plants in 6thWorld Ayurveda Congress, Dec 2010. |
| Employment Record | Employer: Quality Council of India Current Position Held: Director (PPID), QCI Employment Period in Current Organization : 2010 - Present |
| Tasks Undertaken - Qualified internal/ lead auditor for ISO 9000, 14000 and 22000, NPOP, NOP, India GAP, EIA. - Conceptualised and developed new schemes in NABET, fully acquainted with business development, coordination, event planning & management, team building, achievements. - Former programme manager for NPOP, Internal Auditor and system monitoring expert - Technical, Administrative, liaising activities for the Accreditation of Management System training courses, training institutes, sports training centres, Consultant Organisation, ITI, VTP (Vocational Training) Developing the new schemes of accreditations, New initiatives, - Headed and Managed accreditation scheme for EIA consultant organisations and Management system, training programmes new and operational accreditation schemes. Shall be in regular contact with the departments and attend all the meeting as and when required by Client. - Managed voluntary schemes of accreditations, NMPB, IndiGAP, Ayush, Medicinal Healers, |  |

Key Personnel 1:

Key Personnel 2:

| Name of the Organization | Quality Council of India |
| --- | --- |
| Name of Expert | Dr. Manish Pandey |
| Date of Birth | 11.07.1972 |
| Nationality | Indian |
| Highest Education: | Ph.D. (Forest Research Institute, ICFRE- Dehradun) 2000 |
| Membership in Technical Committee of Govt of India (GOI)/ Regulatory Bodies | • Government of India’s technical committee for development of organic standards, accreditation/certification criteria & procedures under National Programme for organic Production (NPOP) • Ministry of Environment and Forest (MoEF) • Technical Advisory Committee of Central Inst. Of Horticulture, Medziphema, Nagaland • Consultative Committee on APEDA’s initiative for traceability in organic through ‘Tracenet’ • QCI sets up a technical committee for develop standard on National Medicinal Plant Board |
| Presentations, Publications & Trainings | • Trainers Training Manual for Sustainable Food System,2001 • Co-Author of Book-Seeds of Suicide: The Ecological and Human Costs of Globalization of Agriculture (2000) • Article on Relevance of Forest Certification in India • Report on the training workshop to assess the Relevance of Introducing Principles of Certification in sectors of Wood Carving and Non-wood Forest. • Research paper on Effect and seed germination, survival in arid zone Guggal (Commiphora wightii Arnott.) under nursery condition. Jor. of Trop., For., Jan-Mar.14 (1) :21-26. |
| Employment Record | Employer: Quality Council of India Current Position Held: Director (PADD), QCI Employment Period in Current Organization: 2011 - Present |
| Tasks Undertaken - Identifying collaborative potential with the Govt. of India, state government, ENGOs viz., WWF, TRAFFIC-India, international organizations like ICRAF, ITTO and other NGOs and regulatory agencies on possibilities of certification, testing and inspection services to aid forest related trade. - Responsible for P & L of Food services for SGS in India achieving + 35% growth YoY - Plan, organized and execute programs to enable supremacy of SGS brand in the Food segment - Plan, organize and execute programs to introduce Global Agriculture services in the Government sector. - Identifying and pursuing Greenfield projects in the Agri-Sector viz. Development of Saffron Park and other related schemes of central and state governments. |  |

| Name of the Organization | Quality Council of India |
| --- | --- |
| Name of Expert | Vikash Singh |
| Date of Birth | 04.07.1977 |
| Nationality | Indian |
| Highest Education: | M.Sc. (Agriculture) with specialization in (Floriculture & Landscaping) from Punjab Agricultural University, 2001 |
| Presentations, Publications & Trainings | Modern trends in rose breeding. |
| Employment Record | Employer: Quality Council of India Current Position Held: Advisor (PPID), QCI Employment Period in Current Organization : Nov 2021 – Present |
|  | Employer: Soloplant Kenya Ltd, Nairobi (Balton CP group). Position Held: General Manager Employment Period: Feb 2020 – Feb 2021 |
|  | Employer: BloomKonnect.com Position Held: Managing Director (Africa Operations) Employment Period: April 2018 – Feb 2020 |
| Worked as an Advisor for the below Projects: - Food Corporation of India transformation project (Grains Procurement Process Audit, Warehouse Assessment and SOP, Modern Warehouse recommendations, Logistics and Movement Optimisation, Tracing and Traceability of Food grains) - IND GAP (India Good Agriculture Practices) for Agriculture Production procedures and quality management. |  |

Key Personnel 3:

Key Personnel 4:

| Name of the Organization | Quality Council of India |
| --- | --- |
| Name of Expert | Dr. Ramanand Shukla |
| Date of Birth | 11.07.1975 |
| Nationality | Indian |
| Highest Education: | Ph. D. in Science, Mumbai University, India,2005; M. Sc. in Mycology & Plant Pathology |
| Membership in Professional Associations | • QCI-NBQP Registered Consultant for HACCP/FSMS, 2016 • Panel Tutor and Lead Auditor for ISO 9001:2008 QMS with British Standards Institution (BSI), 2011 • Member - Expert Group on Food Safety and Quality, CII-FACE, 2010 |
| Presentations, Publications & Trainings | • Certified FSSAI Master Trainer for the statutory training of the Food Safety Officers (FSOs), 2017. • Certified Lead Auditor for ISO 22000:2005 Food Safety Management System, 2009. • Six Sigma Black Belt – AIQM, 2008. • Certified Lead Auditor for ISO 9001:2008 Series Quality Management Systems, 2006. • Train the Trainer – AIQM, 2005. |
| Employment Record | Employer: Quality Council of India Current Position Held: Director (ZED), QCI Employment Period in Current Organization : 2017 - Present |
| Tasks Undertaken - Headed end-to-end responsibilities for the overall quality, environment, health and safety functions on a pan India basis encompassing 250+ branches and formulation plants with a team of cross-functional resources. - Spearheaded Quality Assurance division since 2005; scaled up and professionalized Quality, Environment & Organizational Safety and /Service/Business Excellence function in alignment with organization’s goals/objectives. - Shall be responsible for coordinating with all team members. - Other admin or technical tasks as desired by SG, QCI. - Representing QCI in various national and international platform. |  |