Proposal

CPGRAMS - Project Management Unit (Extension)

Department of Administrative Reforms and Public Grievances

QUALITY COUNCIL OF INDIA

2nd Floor, J Tower, World Trade Centre,

Nauroji Nagar, New Delhi – 110029

T: +91-11-23378056 / 57; F: +91-11-23378678

W: www.qcin.org E: info@qcin.org

# INTRODUCTION

The Department of Administrative Reforms and Public Grievances (DAR&PG), is the nodal agency of the Government of India in-charge of policy making, monitoring and coordinating departments for public grievances. The Allocation of Business Rules, 1961 delineated the mandate for the same. These rules have allocated work relating to (i) redress of public grievances (in general) and (ii) grievances pertaining to Central Government agencies, to the DAR&PG.

One of the key facets of ‘good governance’ is the provision for a platform wherein the citizens can make their grievances known to competent authorities. This century has seen the tremendous impact digitization has had on improved service delivery and ease of access to citizens across sectors and services. Centralized Public Grievance Redress and Monitoring System (CPGRAMS) is another such initiative towards the same.

Centralized Public Grievance Redress and Monitoring System (CPGRAMS) is an online web-enabled system for Pan India grievance registration developed by NIC, in association with Directorate of Public Grievances (DPG) and Department of Administrative Reforms and Public Grievances (DARPG). As per the directions received from Prime Minister’s Office, DARPG undertook CPGRAMS 10-Step Reforms in the year 2022 which were further enhanced in the year 2023. These reforms include, Universalisation of CPGRAMS 7.0. in the Central Secretariat, Technological enhancements using AI/ML, Introduction of regional languages and integration of Bhashini, Grievance Redressal Index for ranking, Feedback Call Centre to collect feedback directly from the citizens, One Nation-One Portal, Increasing Outreach through CSCs, Training and Capacity Building of Grievance Redressal Officers, Monitoring using Monthly Reports and establishment of Data Strategy Unit.

Quality Council of India has worked very closely with DARPG on previous occasions and is familiar with its working and areas of concerns. We started our journey together by conducting numerous grievance studies. In this exercise, QCI intends to gather the information required for building a comprehensive (and thereby streamlined) grievance registration on CPGRAMS and monitoring of the same in order to aid quality and effective disposal of the grievances.

- About Quality Council of India

The Quality Council of India (QCI) has been set up as a non-profit autonomous society registered under Societies Registration Act XXI of 1860 to establish an accreditation structure in the country and to spread quality movement in India by undertaking a National Quality Campaign.

QCI was established as the National body for Accreditation on recommendations of Expert Mission of EU after consultations in Inter-Ministerial Task Force, Committee of Secretaries and Group of Ministers and finally a Cabinet decision in 1996. Accordingly, the Council was made an autonomous non-profit organization through seed funding initially by the Government of India and the Indian Industry represented by the three premier industry associations, Associated Chambers of Commerce and Industry of India (ASSOCHAM), Confederation of Indian Industry (Cll) and Federation of Indian Chambers of Commerce and Industry (FICCI). The Department for Promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry is the nodal point for all matters connected with Quality and QCI.

The Chairman of QCI is nominated by the Hon’ble Prime Minister. QCI was envisaged as an independent organization with its own source of funds through accreditation and activities of quality promotion. It receives limited plan funds for specific promotional activities in quality domain.

The Council was established to create a mechanism for third-party assessment of products, services and processes. In tune with the international best practices, it was envisaged that the Council will play the role of the National Accreditation Body (NAB) as per existing eco-system of quality around the world and will ensure that the quality of life of citizens around the world is improved. It was therefore, befitting that the Council was organized as an independent organization from both government and Industry and functions as an Independent Professional body with its own rules, powers and functions strictly as per the MoA of the society.

- Previous Project Management Units (PMUs) set up by QCI

- Department of Administrative Reforms and Public Grievances (DARPG)

DARPG had asked QCI to setup a PMU for monitoring the implementation of key reforms aimed at reducing public grievances and improving public grievance redressal for the first 20 ministries (previously evaluated by QCI). Apart from the PMU, QCI has worked on grievance analysis of top 40 Ministries/ Departments, revamped the Citizen Charter of CBDT and MEA, revamped CPGRAMS for Top 10 Ministries/ Departments etc.

- NITI Aayog

QCI assisted NITI Aayog to develop and track the Action Plans of 81 Central Government Ministries as requested by the Committee of Secretaries (CoS), an effort led by the Prime Minister of India. QCI is leading the development of a project monitoring portal for real-time analytics and insights for tracking outcomes across Ministries/Departments.

- Ministry of Railways

Ministry of Railways had requested QCI to help drive 9 key budget initiatives and manage their scope and strategy of implementation as well as create a mechanism to monitor their implementation. These initiatives cover a variety of areas from contracts to operations to exports and advertising revenues.

- Ministry of Petroleum and Natural Gas (MoPNG)

MoPNG had requested QCI’s help in creating a tracking, planning and implementation module for Pradhan Mantri Ujjwala Yojana involving:

  - Tracking the scheme implementation, isolating areas with good/bad performance

  - Implementation planning in terms of where to release more connections, where to open more distribution centres etc.

- Objective

The overall objective of setting up the PMU will be to work in association with the DARPG to provide strategy and policy consultation for the Public Grievance Division. The PMU will achieve this by being the nodal point for planning and working on actionable agendas as prioritized by the Department.

- Scope of Work

In 2022, QCI CPGRAMS PMU was set up at DARPG for assisting the Public Grievance Division in monitoring the status of public grievances on the CPGRAMS Portal. A total of 7 work orders has been issued since July, 2022, with the latest one valid till 31st March, 2026.

For the following timelines, the work order has been issued by DARPG to QCI for the CPGRAMS PMU:

| \ | Work Order Issued on | Time Period | Work Order with effective from | Work Order effective till |
| --- | --- | --- | --- | --- |
| 1. | 14th July, 2022 | 1 Year | 14th July, 2022 | 17th July, 2023 |
| 2. | 4th December, 2023 | 6 Months | 18th July, 2023 | 17th January, 2024 |
| 3. | 2nd February, 2024 | 52 Days | 18th January, 2024 | 31st March, 2024 |
| 4. | 13th July, 2024 | 5 Months | 1st April, 2024 | 31st August, 2024 |
| 5. | 29th November, 2024 | 7 Months | 1st September, 2024 | 31st March, 2025 |
| 6. | 13th May, 2025 | 6 Months | 1st April, 2025 | 30th September, 2025 |
| 7. | 21st October, 2025 | 6 Months | 1st October, 2025 | 31st March, 2026 |

The PMU Team will primarily collaborate with the department's PG Division and undertake the following tasks:

- CPGRAMS Monthly Reports:

- Monthly Reports on status of grievances on CPGRAMS for Central Ministries/Departments is compiled after stitching information from various sources like NIC Dashboard, GRAI from CGG Hyderabad, Feedback Data from Call Centre, Tree Dashboard (DSU) and IGMS Dashboard (IIT-Kanpur), etc. Best practices in grievance resolution are highlighted as case studies. [As of March, 2026, the PMU has assisted the department in releasing 46 Monthly Reports for Central Ministries/Departments]

- Monthly Reports on status of grievances on CPGRAMS for States/UTs is compiled after stitching information from sources like NIC Dashboard, etc. Best practices in grievance resolution are highlighted as case studies. [As of March, 2026, the PMU has assisted the department in releasing 43 Monthly Reports for States/UTs]

- CPGRAMS Annual Report:

Annual Report on CPGRAMS is compiled once in a year and is released during the Good Governance Week in December month by MoS PP. (1 per year) [The PMU has assisted the department in releasing the Annual Reports for the year 2022, 2023, 2024 and 2025]

- Presentations:

- Monthly Presentations to be made to the Nodal Officers of Central Ministries/Departments containing a brief overview of pendency and performance on CPGRAMS in a month. (1 per month)

- Monthly Presentations to be made to the Nodal Officers of States/UTs and DGs of ATIs containing a brief overview of pendency and performance on CPGRAMS in a month. Also, highlights the status of grants released under the Sevottam Scheme, and trainings conducted by the State ATIs. (1 per month)

- Presentations to senior officials in Prime Minister’s Office, Cabinet Secretariat, Parliamentary Standing Committee, etc. (as per requirement)

- Presentation to individual Ministry/Department for one-on-one meetings. (as per requirement)

- Presentation for the CSC Live Sessions (as per requirement)

- PIB Statements:

- PIB Statements with the release of the CPGRAMS Monthly Reports for Central Ministries/Departments and States/UTs. (2 per month)

- PIB Statements on the conferences/workshops organised by DARPG (as per requirement)

- Flyers:

Flyers based on CPGRAMS Monthly Reports for Central Ministries/Departments and States/UTs. (2 per month)

- Categorisation:

The team has been working on reviewing and streamlining the existing categorization and mapping across select Central Ministries/Departments by analysing the grievances received in the past few years, taking NIC data into consideration and conducting meetings with the concerned Ministries/Departments to understand their internal structure of grievance handling. [As of March, 2026, the PMU completed the analysis for 39 Ministries/Departments, out of which new categorisation for 31 Ministries/Departments have been made live on the CPGRAMS Portal]

- Social Media Releases:

- Composing material for social media release that highlight CPGRAMS monthly reports.

- Identifying success stories of grievance resolution and releasing it from social media handles of DARPG on a daily basis.

- Composing material for social media release regarding the conferences/workshops organised by DARPG.

- Designing:

Designing of visually appealing banners, cover pages, presentations and a variety of documents to enhance overall communication and presentation. (as per requirement)

- Coordination with other Knowledge Partners of DARPG:

The team has been continuously coordinating with the other stakeholders of the department, including Germanium for Feedback Call Centre, CGG Hyderabad for GRAI Rankings, Data Strategy Unit and IIT-Kanpur for Tree Dashboard and IGMS Dashboard, Common Service Centres, ASCI, etc. for further improvements in the CPGRAMS Portal.

- Coordination with Ministries/Departments/States/UTs:

Resolve queries of the officers from Ministries / Departments / States /UTs on the CPGRAMS Portal and the Grievance Redressal Assessment & Index.

- Capacity Building of Grievance Redressal Officers:

Facilitating the capacity building sessions along with NIC for the grievance redressal officers on CPGRAMS, being organized in DARPG office. Also, visiting Ministry/Department offices as per the requirement for the training.

- Workshops and Conferences:

Assist the department in organizing the National Workshop on Effective Redressal of Public Grievances (Pune – May 2023; Delhi – November 2024; Bhopal – February 2025; Thiruvananthapuram – April 2025; Delhi – July 2025, etc.). Coordinates with all the stakeholders, including speakers, panellist, media team, officers from other Ministry/Department/State/UT, to ensure smooth conduct of the workshop. Collection and compilation of all the presentations, and other documents for the workshop.

The following indicative timeline (for a month) can be followed with respect to the above mentioned points:

| S. No. | Task | W1 | W2 | W3 | W4 |
| --- | --- | --- | --- | --- | --- |
| 1. | CPGRAMS Monthly Report – Central Ministries/Departments |  |  |  |  |
| 2. | CPGRAMS Monthly Report – States/UTs |  |  |  |  |
| 3. | Identifying Success Stories |  |  |  |  |
| 4. | PIB Statements on CPGRAMS Monthly Reports |  |  |  |  |
| 5. | Presentations for Review Meetings with Central Ministries/Departments and States/UTs |  |  |  |  |
| 6. | Flyers on CPGRAMS Monthly Reports for Central Ministries/Departments and States/UTs |  |  |  |  |
| 7. | Categorization |  |  |  |  |
| 8. | Social Media Releases |  |  |  |  |
| 9. | Designing |  |  |  |  |
| 10. | Coordination with Ministries/Departments/States/UTs |  |  |  |  |

The same set of activities will be replicated every month from March, 2026 to March, 2027.

- Support in Implementation of NextGen CPGRAMS:

- The QCI PMU assisted DARPG’s PG Division in reviewing the Functional Requirements Specification (FRS) and System Requirements Specification (SRS) prepared for the NextGen CPGRAMS platform

- The team also provided inputs to align system requirements with operational needs and existing grievance redressal processes under NextGen CPGRAMS

- The team will further support DARPG in the implementation and rollout of the NextGen CPGRAMS platform powered by Artificial Intelligence (AI) and Machine Learning (ML)

- The team will assist in organising stakeholder consultations and workshops with Ministries, Departments, and States to validate requirements and identify areas for improvement, and in conducting training programmes for Grievance Redressal Officers (GROs) on SOP compliance, dashboard usage, and system functionalities

- The team will support the division in preparing user manuals and guidance documents for citizens to improve accessibility and usage of the system

- The team will assist in developing Standard Operating Procedures (SOPs) for Grievance Redressal Officers (GROs) to ensure uniform grievance handling across Ministries and States

- The team will also support the division in developing e-learning modules and blended training formats to improve outreach and accessibility.

- Support in Implementation of AI/ML Chatbot for CPGRAMS:

- Collaborated with DARPG’s knowledge partner in the development of the AI/ML-powered Chatbot for CPGRAMS

- Supported the curation and preparation of relevant datasets required for training the ChatBot

- Undertook testing of ChatBot responses and functionalities to improve its accuracy and usability

- The team will continue to support the division in the implementation and deployment of the AI/ML-powered CPGRAMS Chatbot

- Composition and Manpower

The PMU team will comprise the 3 QCI professionals. The Department will assign a Single Point of Contact (SPOC) for smooth coordination on project requirements. The professionals will have the relevant qualifications and professional background required to fulfil the tasks outlined in the previous section.

These professionals shall have the following skills and credentials:

- The Project lead must have worked at QCI for at least 1 year and shall have a direct line of reporting to Chairman and Secretary General, QCI

- The professionals might have been a part of any earlier PMU’s set up at various Ministries/Departments by QCI

- To provide assistance with specific analysis, at least 1 professional should have core expertise in data analytics and must have graduated from Tier 1 college from India/abroad

- Review

A quarterly review may be conducted for the PMU. The composition of the review panel may be decided by the DARPG. The broad role of the review panel may be as follows:

- Conduct monthly progress reviews for the 3 QCI professionals

- The review panel may choose to re-focus the QCI team onto a different part of the pre-agreed upon scope if they feel it might add more value. The panel and the QCI team may mutually agree upon the revised direction for the project

- Debottlenecking of any major hurdles faced during the project

- Financials

The financials for the extension of the PMU for a period of one year are as follows:

| DARPG – CPGRAMS Project Monitoring Unit |  |  |  |  |
| --- | --- | --- | --- | --- |
| Quality Council of India |  |  |  |  |
| Activity | Man Days | Number of Resources | Cost / Man Day | Total Cost |
| QCI Professional | 260 (5 * 52 weeks) | 3 | Rs. 8,250# | Rs. 64,35,000 |
| QCI (Administration cost) | 12% of total cost |  |  | Rs. 7,72,200 |
| Total Cost (A) |  |  |  | Rs. 72,07,200 |

GST to be charged separately.

#The man-day cost has been revised upward by 10% compared to the previously submitted proposal. This revision has been made to account for prevailing market inflation and the increase in employee compensation, including salaries and associated benefits provided by the organisation. The adjustment ensures that the costing remains aligned with current market conditions and organisational compensation policies, while enabling the continued engagement of qualified personnel for effective project execution.

Note:

- Attendance, leave, and related service conditions of the PMU resources deployed at DARPG shall be governed by the internal policies and procedures of the Quality Council of India. However, the PMU personnel shall keep the concerned officers at DARPG duly informed in advance regarding any leave or work-from-home arrangements to ensure continuity of work and coordination.

- In an event, for which travel or commute outside of team’s designated location (New Delhi) is necessary, travel and accommodation facility to be provided to the PMU Team by DARPG.

The new work order will be applicable from 1st April, 2026, for a period of one year, till 31st March, 2027.

- Payment Structure

The payment structure may be as follows:

| S. No. | Target, Milestone, or Reporting Deliverables | Amount (%) |
| --- | --- | --- |
| 1 | Completion of 1 Month | 9% |
| 2 | Completion of 2 Months | 8% |
| 3 | Completion of 3 Months | 8% |
| 4 | Completion of 4 Months | 9% |
| 5 | Completion of 5 Months | 8% |
| 6 | Completion of 6 Months | 8% |
| 7 | Completion of 7 Months | 9% |
| 8 | Completion of 8 Months | 8% |
| 9 | Completion of 9 Months | 8% |
| 10 | Completion of 10 Months | 9% |
| 11 | Completion of 11 Months | 8% |
| 12 | Completion of 12 Months | 8% |
| Total |  | 100% |

- Obligations and asks from the DARPG

To ensure the program starts and progresses smoothly, QCI requests the DARPG to facilitate the QCI team with the following:

- Issue a sanction order to QCI with the following aspects:

  - Formal extension date for PMU team

  - Finalised terms of payment

  - Detailed work order to include final cost accepted by the DARPG

  - Details of Initiatives and projects to be covered by the PMU

  - Finalisation of the PMU’s overall statement of work

- Creation of review committee, including finalisation of structure, powers and personnel on the committee

- Nominate a Single Point of Contact (SPOC) for various functions in DARPG for coordination with PMU to assist in cross-functional collaboration

- Finalisation of initiative scope to be done between QCI team and relevant SPOC before the start of the project

- In addition, a note is to be sent to all relevant stakeholders stating QCI’s involvement to ensure cooperation

- Provision of 1 room within DARPG premises for project team members from QCI to sit. The room should have adequate seating for all QCI personnel and DARPG personnel deputed within the PMU. Printing, Wi-Fi and other facilities necessary should also be provided to the PMU team by the DARPG.

- Entry-pass for all project team members for the duration of project to be issued

- Terms and Conditions

- Exit Clause

In case either party does not wish to continue with the project, expenses and project payment till date of continuation will be paid to Quality Council of India. The finalised exit route will be decided upon to finalise handover of responsibilities. Official termination of services will be brought into effect 3 weeks from notification of exit.

- Dispute Resolution

Any dispute will be resolved by mutual agreement.

- Undertakings

- Data Confidentiality

QCI will ensure confidentiality of all data, presentations, reports etc. prepared during the project and will not release the above to any other QCI team members except the three professionals engaged with the DARPG as well as any 3rd parties until prior discussion and agreement with the DARPG.

- Payment

DARPG will ensure all required payments and reimbursements to Quality Council of India will be made in a timely manner.

- Service Charge

Service charges (as applicable) will be paid by the DARPG in addition to the cost specified in the proposal above.