Proposal

CPGRAMS - Project Management Unit (Extension)

Department of Administrative Reforms and Public Grievances

QUALITY COUNCIL OF INDIA

2nd Floor, J Tower, World Trade Centre,

Nauroji Nagar, New Delhi – 110029

T: +91-11-23378056 / 57; F: +91-11-23378678

W: www.qcin.org E: info@qcin.org

# INTRODUCTION

The Department of Administrative Reforms and Public Grievances (DAR&PG), is the nodal agency of the Government of India in-charge of policy making, monitoring and coordinating departments for public grievances. The Allocation of Business Rules, 1961 delineated the mandate for the same. These rules have allocated work relating to (i) redress of public grievances (in general) and (ii) grievances pertaining to Central Government agencies, to the DAR&PG.

One of the key facets of ‘good governance’ is the provision for a platform wherein the citizens can make their grievances known to competent authorities. This century has seen the tremendous impact digitization has had on improved service delivery and ease of access to citizens across sectors and services. Centralized Public Grievance Redress and Monitoring System (CPGRAMS) is another such initiative towards the same.

Centralized Public Grievance Redress and Monitoring System (CPGRAMS) is an online web-enabled system for Pan India grievance registration developed by NIC, in association with Directorate of Public Grievances (DPG) and Department of Administrative Reforms and Public Grievances (DARPG). As per the directions received from Prime Minister’s Office, DARPG undertook CPGRAMS 10-Step Reforms in the year 2022 which were further enhanced in the year 2023. These reforms include, Universalisation of CPGRAMS 7.0. in the Central Secretariat, Technological enhancements using AI/ML, Introduction of regional languages and integration of Bhashini, Grievance Redressal Index for ranking, Feedback Call Centre to collect feedback directly from the citizens, One Nation-One Portal, Increasing Outreach through CSCs, Training and Capacity Building of Grievance Redressal Officers, Monitoring using Monthly Reports and establishment of Data Strategy Unit.

Quality Council of India has worked very closely with DARPG on previous occasions and is familiar with its working and areas of concerns. We started our journey together by conducting numerous grievance studies. In this exercise, QCI intends to gather the information required for building a comprehensive (and thereby streamlined) grievance registration on CPGRAMS and monitoring of the same in order to aid quality and effective disposal of the grievances.

- About Quality Council of India

The Quality Council of India (QCI) has been set up as a non-profit autonomous society registered under Societies Registration Act XXI of 1860 to establish an accreditation structure in the country and to spread quality movement in India by undertaking a National Quality Campaign.

QCI was established as the National body for Accreditation on recommendations of Expert Mission of EU after consultations in Inter-Ministerial Task Force, Committee of Secretaries and Group of Ministers and finally a Cabinet decision in 1996. Accordingly, the Council was made an autonomous non-profit organization through seed funding initially by the Government of India and the Indian Industry represented by the three premier industry associations, Associated Chambers of Commerce and Industry of India (ASSOCHAM), Confederation of Indian Industry (Cll) and Federation of Indian Chambers of Commerce and Industry (FICCI). The Department for Promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry is the nodal point for all matters connected with Quality and QCI.

The Chairman of QCI is nominated by the Hon’ble Prime Minister. QCI was envisaged as an independent organization with its own source of funds through accreditation and activities of quality promotion. It receives limited plan funds for specific promotional activities in quality domain.

The Council was established to create a mechanism for third-party assessment of products, services and processes. In tune with the international best practices, it was envisaged that the Council will play the role of the National Accreditation Body (NAB) as per existing eco-system of quality around the world and will ensure that the quality of life of citizens around the world is improved. It was therefore, befitting that the Council was organized as an independent organization from both government and Industry and functions as an Independent Professional body with its own rules, powers and functions strictly as per the MoA of the society.

- Previous Project Management Units (PMUs) set up by QCI

- Department of Administrative Reforms and Public Grievances (DARPG)

DARPG had asked QCI to setup a PMU for monitoring the implementation of key reforms aimed at reducing public grievances and improving public grievance redressal for the first 20 ministries (previously evaluated by QCI). Apart from the PMU, QCI has worked on grievance analysis of top 40 Ministries/ Departments, revamped the Citizen Charter of CBDT and MEA, revamped CPGRAMS for Top 10 Ministries/ Departments etc.

- NITI Aayog

QCI assisted NITI Aayog to develop and track the Action Plans of 81 Central Government Ministries as requested by the Committee of Secretaries (CoS), an effort led by the Prime Minister of India. QCI is leading the development of a project monitoring portal for real-time analytics and insights for tracking outcomes across Ministries/Departments.

- Ministry of Railways

Ministry of Railways had requested QCI to help drive 9 key budget initiatives and manage their scope and strategy of implementation as well as create a mechanism to monitor their implementation. These initiatives cover a variety of areas from contracts to operations to exports and advertising revenues.

- Ministry of Petroleum and Natural Gas (MoPNG)

MoPNG had requested QCI’s help in creating a tracking, planning and implementation module for Pradhan Mantri Ujjwala Yojana involving:

  - Tracking the scheme implementation, isolating areas with good/bad performance

  - Implementation planning in terms of where to release more connections, where to open more distribution centres etc.

- Objective

The overall objective of setting up the PMU will be to work in association with the DARPG to provide strategy and policy consultation for the Public Grievance Division. The PMU will achieve this by being the nodal point for planning and working on actionable agendas as prioritized by the Department.

- Scope of Work

In July, 2022, the QCI CPGRAMS PMU was set up at DARPG for assisting the Public Grievance Division in monitoring the status of public grievances on the CPGRAMS Portal. A total of 6 work orders has been issued since July, 2022, with the latest one valid till 30th September, 2025.

For the following timelines, the work order has been issued by DARPG to QCI for the CPGRAMS PMU:

| S. No. | Work Order Issued on | Time Period | Work Order with effective from | Work Order effective till |
| --- | --- | --- | --- | --- |
| 1. | 14th July, 2022 | 1 Year | 14th July, 2022 | 17th July, 2023 |
| 2. | 4th December, 2023 | 6 Months | 18th July, 2023 | 17th January, 2024 |
| 3. | 2nd February, 2024 | 52 Days | 18th January, 2024 | 31st March, 2024 |
| 4. | 13th July, 2024 | 5 Months | 1st April, 2024 | 31st August, 2024 |
| 5. | 29th November, 2024 | 7 Months | 1st September, 2024 | 31st March, 2025 |
| 6. | 13th May, 2025 | 6 Months | 1st April, 2025 | 30th September, 2025 |

The PMU Team will primarily collaborate with the department's PG Division and undertake the following tasks:

- Periodic Tasks:

| S. No. | Deliverable | Remarks |
| --- | --- | --- |
| 1. | CPGRAMS Monthly Reports | Monthly Reports on status of grievances on CPGRAMS for Central Ministries/Departments is compiled after stitching information from various sources like NIC Dashboard, GRAI from CGG Hyderabad, Feedback Data from Call Centre, Tree Dashboard (DSU) and IGMS Dashboard (IIT-Kanpur), etc. Best practices in grievance resolution are highlighted as case studies. [As of September, 2025, the PMU has assisted the department in releasing 40 Monthly Reports for Central Ministries/Departments] |
|  |  | Monthly Reports on status of grievances on CPGRAMS for States/UTs is compiled after stitching information from sources like NIC Dashboard, etc. Best practices in grievance resolution are highlighted as case studies. [As of September, 2025, the PMU has assisted the department in releasing 37 Monthly Reports for States/UTs] |
| 2. | Annual Report | Annual Report on CPGRAMS is compiled once in a year and is released during the Good Governance Week in December month by MoS PP. (1 per year) [The PMU has assisted the department in releasing the Annual Reports for the year 2022, 2023 and 2024] |
| 3. | Presentations | Monthly Presentations to be made to the Nodal Officers of Central Ministries/Departments containing a brief overview of pendency and performance on CPGRAMS in a month. (1 per month) |
|  |  | Monthly Presentations to be made to the Nodal Officers of States/UTs and DGs of ATIs containing a brief overview of pendency and performance on CPGRAMS in a month. Also, highlights the status of grants released under the Sevottam Scheme, and trainings conducted by the State ATIs. (1 per month) |
|  |  | Presentation to individual Ministry/Department for one-on-one meetings. (as per requirement) |
|  |  | Presentation for the CSC Live Sessions (as per requirement) |
|  |  | Presentations to senior officials in Prime Minister’s Office, Cabinet Secretariat, Parliamentary Standing Committee, etc. (as per requirement) |
| 4. | PIB Statements | PIB Statements with the release of the CPGRAMS Monthly Reports for Central Ministries/Departments and States/UTs. (2 per month) |
|  |  | PIB Statements on the conferences/workshops organised by DARPG (as per requirement) |
|  |  | PIB Statements on the success stories of grievance resolution by Central Ministries/Departments and States/UTs. (as per requirement) |
| 5. | Flyers | Flyers based on CPGRAMS Monthly Reports for Central Ministries/Departments and States/UTs. (2 per month) |
| 6. | Monitoring of Call Centre Data | Compilation of Feedback Call Centre Reports and Data, and coordinate with the call centre team for continuous improvement in the operations. |
| 7. | Categorization | The team has been working on reviewing and streamlining the existing categorization and mapping across select Central Ministries/Departments by analysing the grievances received in the past few years, taking NIC data into consideration and conducting meetings with the concerned Ministries/Departments to understand their internal structure of grievance handling. [As of September, 2025, the PMU completed the analysis for 31 Ministries/Departments, out of which new categorisation for 25 Ministries/Departments have been made live on the CPGRAMS Portal] |
| 8. | Root Cause Analysis | Conducted root cause analysis of grievances and identified key patterns contributing to recurring issues. Based on the findings, systemic reforms have been suggested to enhance grievance redressal efficiency. (as per requirement) |
| 9. | Taxonomy Analysis | Refined and cleaned data from the Tree dashboard to facilitate a comprehensive taxonomy analysis of the Ministries/Departments (as per requirement. The analysis is being released in the CPGRAMS Monthly Reports for Central Ministries/Departments. |
| 10. | Social Media Releases | Composing material for social media release that highlighted monthly reports and success stories. |
|  |  | Composing material for social media release regarding the conferences/workshops organised by DARPG. |
| 11. | Designing | Designing of visually appealing banners, cover pages, presentations and a variety of documents to enhance overall communication and presentation. (as per requirement) |
| 12. | Coordination with other Knowledge Partners of DARPG | The team has been continuously coordinating with the other stakeholders of the department, including Germanium for Feedback Call Centre, CGG Hyderabad for GRAI Rankings, Data Strategy Unit and IIT-Kanpur for Tree Dashboard and IGMS Dashboard, Common Service Centres, ASCI, etc. for further improvements in the CPGRAMS Portal. |
| 13. | Coordination with Ministries / Departments / States / UTs | Resolve queries of the officers from Ministries / Departments / States /UTs on the CPGRAMS Portal. |
| 14. | Capacity Building of GROs | Facilitating the capacity building sessions along with NIC for the grievance redressal officers on CPGRAMS, being organized in DARPG office. Also, visiting Ministry/Department offices as per the requirement for the training. |
| 15. | Workshops and Conferences | Assist the department in organizing the National Workshop on Effective Redressal of Public Grievances (Pune – May 2023; Delhi – November 2024; Bhopal – February 2025; Thiruvananthapuram – April 2025; Delhi – July 2025, etc.). Coordinates with all the stakeholders, including speakers, panellist, media team, officers from other Ministry/Department/State/UT, to ensure smooth conduct of the workshop. Collection and compilation of all the presentations, and other documents for the workshop. |

The following indicative timeline (for a month) can be followed with respect to the above mentioned points:

| S. No. | Task | W1 | W2 | W3 | W4 |
| --- | --- | --- | --- | --- | --- |
| 1. | CPGRAMS Monthly Report – Central Ministries/Departments |  |  |  |  |
| 2. | CPGRAMS Monthly Report – States/UTs |  |  |  |  |
| 3. | Identifying Success Stories |  |  |  |  |
| 4. | PIB Statements on CPGRAMS Monthly Reports and Success Stories |  |  |  |  |
| 5. | Presentations for Review Meetings with Central Ministries/Departments and States/UTs |  |  |  |  |
| 6. | Flyers on CPGRAMS Monthly Reports for Central Ministries/Departments and States/UTs |  |  |  |  |
| 7. | Categorization |  |  |  |  |
| 8. | Root Cause Analysis |  |  |  |  |
| 9. | Taxonomy Analysis |  |  |  |  |
| 10. | Social Media Releases |  |  |  |  |
| 11. | Designing |  |  |  |  |
| 12. | Coordination with Ministries/Departments/States/UTs |  |  |  |  |

The same set of activities will be replicated every month from October, 2025 to March, 2026.

Going forward, DARPG is set to launch a NextGen CPGRAMS architecture that leverages Machine Learning and Artificial Intelligence. QCI CPGRAMS PMU assisted the other knowledge partner of DARPG developing the RFP for Next-Gen CPGRAMS, in understanding functioning of the CPGRAMS Portal, which created a base for the Next-Gen CPGRAMS. QCI team also assisted the PG Division in reviewing the FRS and SRS Documents prepared for the NextGen CPGRAMS. Additionally, QCI team also assisted the other knowledge partner of DARPG to develop the AI/ML Chatbot for CPGRAMS, by curating the relevant datasets.

- NextGen CPGRAMS:

- Conduct gap analysis of NextGen documentation and validate through stakeholder workshops

- Process standardisation & quality assurance through drafting SOPs for GROs and user manuals for citizens to ensure uniform adoption, defining measurable KPIs for monitoring performance, piloting SOPs and KPIs in select Ministries/States to test compliance and data quality, and conducting user testing to identify gaps in usability and efficiency

- Data analytics & insights to track trends and categorisation accuracy, predictive analytics to move from reactive to proactive governance, and benchmarking reports that combine quantitative and qualitative measures such as redressal quality and citizen satisfaction. These insights will enable systemic improvements, targeted training, and policy-level interventions while auto-flagging persistent delays for corrective action

- Impact evaluation studies to identify systemic issues from grievance patterns to generate policy-level insights, enabling evidence-based reforms across Ministries and States

- Capacity building & institutional strengthening will involve tiered training programs for GROs, and citizens to build system familiarity and process efficiency. QCI can deliver strategic modules for senior officials, hands-on workshops for GROs and SOP compliance, and awareness campaigns for citizens to improve adoption. Training interventions will include conducting needs assessments to tailor content, developing e-learning and blended modules, and implementing train-the-trainer programs for wider reach. Continuous feedback loops and performance monitoring will ensure improved grievance handling, dashboard usage, and SOP compliance over time

- NextGen CPGRAMS transition & adoption can leverage QCI PMU’s deep domain knowledge and strong stakeholder relationships to facilitate smooth configuration and rollout. By mapping Ministry-specific needs to NextGen features, recommending optimal configurations, and developing tailored adoption plans, QCI will ensure policy compliance, operational efficiency, and continuity of legacy data. This alignment with DARPG objectives will enable measurable improvements in user experience, resolution efficiency, and accountability.

- Composition and Manpower

The PMU team will comprise the 3 QCI professionals. The Department will assign a Single Point of Contact (SPOC) for smooth coordination on project requirements. The professionals will have the relevant qualifications and professional background required to fulfil the tasks outlined in the previous section.

These professionals shall have the following skills and credentials

- The Project lead must have worked at QCI for at least 1 year and shall have a direct line of reporting to Chairman and Secretary General, QCI

- The professionals might have been a part of any earlier PMU’s set up at various Ministries/Departments by QCI

- To provide assistance with specific analysis, at least 1 professional should have core expertise in data analytics and must have graduated from Tier 1 college from India/abroad

- Review

A quarterly review may be conducted for the PMU. The composition of the review panel may be decided by the DARPG. The broad role of the review panel may be as follows:

- Conduct monthly progress reviews for the 3 QCI professionals

- The review panel may choose to re-focus the QCI team onto a different part of the pre-agreed upon scope if they feel it might add more value. The panel and the QCI team may mutually agree upon the revised direction for the project

- Debottlenecking of any major hurdles faced during the project

- Financials

The financials have been kept as per the previous work orders, for the extension of the PMU by QCI as follows:

| DARPG – CPGRAMS Project Monitoring Unit |  |  |  |  |
| --- | --- | --- | --- | --- |
| Quality Council of India |  |  |  |  |
| Activity | Man Days | Number of Resources | Cost / Man Day | Total Cost |
| QCI Professional | 120 | 3 | Rs. 7,500 | Rs. 27,00,000 |
| QCI (Administration cost) | 12% of total cost |  |  | Rs. 3,24,000 |
| Total Cost (A) |  |  |  | Rs. 30,24,000 |

*GST to be charged separately

The new work order will be applicable from 1st October, 2025, for a period of 6 months, till 31st March, 2026.

- Payment Structure

The payment structure may be as follows:

| S. No. | Target, Milestone, or Reporting Deliverables | Amount (%) |
| --- | --- | --- |
| 1 | Completion of 1 Month | 20% |
| 2 | Completion of 2 Months | 20% |
| 3 | Completion of 3 Months | 15% |
| 4 | Completion of 4 Months | 15% |
| 5 | Completion of 5 Months | 15% |
| 6 | Completion of 6 Months | 15% |
| Total |  | 100% |

- Obligations and asks from the DARPG

To ensure the program starts and progresses smoothly, QCI requests the DARPG to facilitate the QCI team with the following:

- Issue a sanction order to QCI with the following aspects:

  - Formal extension date for PMU team

  - Finalised terms of payment

  - Detailed work order to include final cost accepted by the DARPG

  - Details of Initiatives and projects to be covered by the PMU

  - Finalisation of the PMU’s overall statement of work

- Creation of review committee, including finalisation of structure, powers and personnel on the committee

- Nominate a Single Point of Contact (SPOC) for various functions in DARPG for coordination with PMU to assist in cross-functional collaboration

- Finalisation of initiative scope to be done between QCI team and relevant SPOC before the start of the project

- In addition, a note is to be sent to all relevant stakeholders stating QCI’s involvement to ensure cooperation

- Provision of 1 room within DARPG premises for project team members from QCI to sit. The room should have adequate seating for all QCI personnel and DARPG personnel deputed within the PMU. Printing, Wi-Fi and other facilities necessary should also be provided to the PMU team by the DARPG.

- Entry-pass for all project team members for the duration of project to be issued

- In an event, for which travel or commute outside of team’s designated location (New Delhi) is necessary, travel and accommodation facility to be provided to the PMU Team by DARPG

- Terms and Conditions

- Exit Clause

In case either party does not wish to continue with the project, expenses and project payment till date of continuation will be paid to Quality Council of India. The finalised exit route will be decided upon to finalise handover of responsibilities. Official termination of services will be brought into effect 3 weeks from notification of exit.

- Dispute Resolution

Any dispute will be resolved by mutual agreement.

- Undertakings

- Data Confidentiality

QCI will ensure confidentiality of all data, presentations, reports etc. prepared during the project and will not release the above to any other QCI team members except the six professionals engaged with the DARPG as well as any 3rd parties until prior discussion and agreement with the DARPG.

- Payment

DARPG will ensure all required payments and reimbursements to Quality Council of India will be made in a timely manner.

- Service Charge

Service charges (as applicable) will be paid by the DARPG in addition to the cost specified in the proposal above.